# Columbia River System (CRS) Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District (NWP) and Walla Walla District (NWW)

April 2025 Written Update

FFDRWG Files: https://public.crohms.org/tmt/documents/FPOM/2010/FFDRWG/CY2025/

# FFDRWG contact list - ** notify Chuck and Jake of any changes

BPA

Christine Petersen

Leah Sullivan

Ben Hausmann

Carolina Andes

Josh Ashline

Tammy Mackey

NOAA

Gabriel Brooks

Trevor Conder

Claire McGrath

Kelsey Swieca

Chris Magel

Kinsey Frick

Dana Bethea

USFWS

Dave Swank

Shelby Fowler

Joe Skalicky

States

Erick Van Dyke (ODFW)

Ben Clemens (ODFW)

C. Morrill (WDFW)

Jonathan Ebel (IDFG)

Marika Dobos (IDFG)

CRITFC/Tribes

Tom Lorz (CRITFC)

Laurie Porter (CRITFC)

Greg Silver (CRITFC)

Aaron Jackson (CTUIR)

Ralph Lampman (YN)

Keely Murdoch (YN)

Tod Sween (NPT)

Jay Hesse (NPT)

Lyman Jim (CTWS)

Casey Baldwin (CTCR)

Michael Karnosh (CTGR)

Lawrence Schwabe (CTGR)

Torey Wakeland (CTGR)

NPCC

Kris Homel

Kate Self

FPC

Erin Cooper

Noah Campbell

PSMFC

Gordy Axel

Darren Chase

Roger Clark

Mark Leonard

Scott Livingston

Nicole Tancreto

CENWD

Doug Baus

Tim Dykstra

Dan Feil

Cindy Studebaker

Lisa Wright

Sean Tackley

Ian Chane

CENWP-PM

Ida Royer

Erin Kovalchuk

Mark Bierman

Nathan McClain

Jake Macdonald

Marie Adams

Jon Rerecich

David Trachtenbarg

Scott Fielding

Courtney Hollins

CENWP-OD

Nick Bertrand (ODT)

Jeanette Flemmer (BON)

Tucker Gossett (BON)

Jase Owens (BON)

Becca Cates (BON)

Eric Grosvenor (TDA)

Jeff Randall (TDA)

Aaron Young (TDA)

David Miller (JDA)

Michael Lotspeich (JDA)

Laura Rickets (JDA)

Robert Wertheimer (FFU)

Patricia Madson (FFU)

Darren Gallion (FFU)

Kyle Tidwell (FFU)

CENWP-ENC

Aaron Litzenberg (HD)

Shari Dunlop (HD)

Chris Motti (HD)

Steve Schlenker (HD)

Max Wilson-Fey (HD)

Adam White (DE)

Collin Porter (DS)

Dan Penn (DM)

Cole Marfise (DM)

Adam Jones (DG)

Nicholas Rillstone (DS)

CENWW-PM

Chuck Barnes

Ryan Ashcraft

Steve Sipe

Ricardo Walker

Brad Trumbo

Liana Aker

Michael Erickson

Karen Zelch

Kathryn Herzog

CENWW-OD

Chris Peery

Tiffany Stoeckig-Dixon

Denise Griffith

Elizabeth Holdren

Ken Fone

Bobby Johnson

Deb Snyder

CENWW-ENC

Jon Renholds

Sean Milligan

Ryan Pestes

Travis Foster

John Lomeland

Ryan Laughery

# Review Notes from last meeting (6 March)

# NWW Updates

## NWW MNA Turbine Replacement Design – Jean Desjarlais (PM), Jon Renholds (TL)

No new updates to report. Next discussion will be on operation range of new adjustable units at June FFDRWG meeting.

## NWW IHR Turbine Cooling Water Exclusion - Karen Zelch (PM), Chuck Barnes (Bio)

Still analyzing monthly strainer counts. Possible ROV inspection upcoming to ensure structure is in place as intended.

## NWW LLA Adult Ladder Turn Pool Gate - Greg Linklater (PM), Chuck Barnes (Bio)

Scheduled for install next winter work window.

## NWW MCN Avian deterrence – Karen Zelch (PM), Ryan Ashcraft (Bio)

Draft conceptual design report will be sent to FFDRWG for review at the end of May.

## NWW MNA PIT Detection – Kat Herzog (PM), Chuck Barnes (FFDRWG)

### 3/20/25 PIT Detection Screening Workshop

Workshop notes distributed 3/28 along with historic MNA PIT detection analysis. Comments on notes and any other input or recommendations from workshop due 4/18. Further discussion on workshop results and comment responses at May FFDRWG meeting.

## NWW John Day Dam and Snake River Ladder Cooling – Karen Zelch (PM), Ryan Laughery (TL), Ryan Ashcraft (FFDRWG)

Workshop with FFDRWG group scheduled for May 7th.

# NWP Updates

## NWP JDA South fish pumps - Dave Hamernik (PM), JDA Fisheries (FFDRWG)

### Short-term interim repairs (O&M/FPOM)

### Long-term full replacement of all three pumps (SCT/FFDRWG)

seeking CRFM funding for full replacement of all three pumps in an out year

## NWP TDA Backup AWS debris management – Marie Adams (PM), Mehdi Roshani (TL), Nathan McClain (FFDRWG)

Email from Nathan McClain on 3/25.  90% submittals are available for FFDRWG review on the FFDRWG Files website.  Comments due 4/18.

## NWP BON Spillway rock mitigation – Marie Adams (PM), Adam Jones (TL), Jake Macdonald (FFDRWG)

Not currently on track for construction this Winter. Waiting for O&M funding to match BPA funding.

## Bradford Island and Cascades Island LPS pump upgrades (Kovalchuk/White)

Ordering materials in 2025, installation by Project staff winter 2025-2026.

## NWP BON1 Ice & Trash PIT Detection – Mark Bierman (PM), Jeanette Flemmer (FFDRWG)

Less than 1-day installation in late June or early July 2025

## NWP BON2 control section redesign – Erin Kovalchuk (PM), Adam White (TL), Jake Macdonald (FFDRWG)

### Exit channel PIT detection for post-construction evaluation

NMFS/PSMFC are finishing fabrication, but prioritizing resources on BO4.  BO4 will be complete in April and the new exit channel antenna for this post-construction evaluation will be installed in May.

## NWP BON2 junction pool lamprey trap/LPS - Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Funding dependent/subject to change: EDR in 2025, DDR in 2026, P&S in 2027, construction Winter 28-29

## NWP TDA North lamprey passage structure extension for volitional passage – Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Funding dependent/subject to change: EDR in 2025, DDR in 2026, P&S in 2027, construction Winter 27-28

## NWP JDA North lamprey passage structure extension for volitional passage – Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Funding dependent/subject to change: EDR in 2025, DDR in 2026, P&S in 2027, construction Winter 27-28

## NWP JDA North lamprey passage structure water supply improvements – Courtney Hollins (PM), Stacy Jensen (TL), JDA Fisheries (FFDRWG)

Contract award is imminent.  Any construction activity near the fish ladder proposed during the 2025 passage season will be coordinated in FPOM.

## NWP prototype floating adult lamprey collector for tribal translocation, aka. “FALCON” (*partner project; not a USACE design) – Ralph Lampman (TL), Jake Macdonald (FFDRWG)

deployment plan for prototype testing in the Bonneville tailrace in July 2025 will be proposed at FPOM.

# Upcoming meetings and field trips

## Fish Facilities Design Review Work Group (FFDRWG) = first Thursday of every month (contact Jake Macdonald and Chuck Barnes if you need an invitation).

### Thursday 5/1/25 @ 09:00

## Fish Passage Operation & Maintenance (FPOM) Work Group = second Thursday of every month = (contact Patricia Madson and Chris Peery if you need an invitation).

### Thursday 4/10/25 @ 09:00 and Thursday 5/8/25 @ 09:00

## Studies Review Work Group (SRWG) FY 2026 Planning Cycle: https://public.crohms.org/tmt/documents/FPOM/2010/SRWG/FY26AFEPplanning/

### FY26 SRWG planning cycle kickoff meeting - Tuesday 2/18/25.

### FY26 SRWG research summary review and development meeting – Thursday 3/6/25.

### FY26 SRWG research summary scoring meeting – Friday 5/2/25.  Location: TBD

### FY26 SRWG preliminary proposal review meeting – Thursday 7/3/25.  Location: TBD

### FY26 SRWG final proposal review meeting – Friday 8/29/25.  Location: TBD

## Upcoming Field Trips: