# Columbia River System (CRS) Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District (NWP) and Walla Walla District (NWW)

September 2025 Agenda

FFDRWG Files: https://public.crohms.org/tmt/documents/FPOM/2010/FFDRWG/CY2025/

# FFDRWG contact list - ** notify Chuck and Jake of any changes

BPA

Christine Petersen

Leah Sullivan

Ben Hausmann

Carolina Andes

Josh Ashline

Tammy Mackey

NOAA

Trevor Conder

Kelsey Swieca

Chris Magel

Emi Melton

Kinsey Frick

USFWS

Dave Swank

Shelby Fowler

Joe Skalicky

States

Erick Van Dyke (ODFW)

Ben Clemens (ODFW)

C. Morrill (WDFW)

Jonathan Ebel (IDFG)

Marika Dobos (IDFG)

CRITFC/Tribes

Tom Lorz (CRITFC)

Laurie Porter (CRITFC)

Greg Silver (CRITFC)

Pete McHugh (CRITFC)

Aaron Jackson (CTUIR)

Ralph Lampman (YN)

Keely Murdoch (YN)

Tod Sween (NPT)

Jay Hesse (NPT)

Lyman Jim (CTWS)

Casey Baldwin (CTCR)

Michael Karnosh (CTGR)

Lawrence Schwabe (CTGR)

Torey Wakeland (CTGR)

NPCC

Kris Homel

Kate Self

FPC

Erin Cooper

Noah Campbell

PSMFC

Gordy Axel

Darren Chase

Roger Clark

Mark Leonard

Scott Livingston

Nicole Tancreto

CENWD

Doug Baus

Tim Dykstra

Dan Feil

Cindy Studebaker

Lisa Wright

Sean Tackley

Ian Chane

CENWP-PM

Ida Royer

Erin Kovalchuk

Mark Bierman

Jake Macdonald

Marie Adams

David Trachtenbarg

Courtney Hollins

CENWP-OD

Nick Bertrand (ODT)

Jeanette Wendler (BON)

Tucker Gossett (BON)

Jase Owens (BON)

Becca Cates (BON)

Eric Grosvenor (TDA)

Jeff Randall (TDA)

Aaron Young (TDA)

David Miller (JDA)

Michael Lotspeich (JDA)

Laura Rickets (JDA)

Robert Wertheimer (FFU)

Patricia Madson (FFU)

Darren Gallion (FFU)

Kyle Tidwell (FFU)

CENWP-ENC

Aaron Litzenberg (HD)

Shari Dunlop (HD)

Chris Motti (HD)

Steve Schlenker (HD)

Max Wilson-Fey (HD)

Adam White (DE)

Collin Porter (DS)

Dan Penn (DM)

Cole Marfise (DM)

Adam Jones (DG)

Nicholas Rillstone (DS)

Will Guest (DS)

CENWW-PM

Chuck Barnes

Ryan Ashcraft

Ricardo Walker

Brad Trumbo

Kathryn Herzog

Jeremy Nguyen

Karen Kelly

CENWW-OD

Chris Peery

Tiffany Stoeckig-Dixon

Denise Griffith

Bobby Johnson

Deb Snyder

Steven Lee

CENWW-ENC

Jon Renholds

Ryan Pestes

Travis Foster

Ryan Laughery

# NWP/NWW Updates

## NWP JDA South fish pumps - Tim Ernster (PM), JDA Fisheries (FFDRWG)

### Short-term interim repairs (O&M/FPOM)

### Long-term full replacement of all three pumps (CRFM/FFDRWG)

Reminder of FFDRWG concerns related to sequencing of JDA fish pumps and JDA turbine replacement (Andes, BPA)

## NWP TDA Backup AWS debris management – Marie Adams (PM), Mehdi Roshani (TL), Jake Macdonald (FFDRWG)

90% DDR completed April 2025.  Next milestone is plans & specs. Eric Grosvenor: On Pause.

Chris Magel: Comments were provided. Will there be a review of those or comment responses provided?

- Eric Grosvenor: Responses should be on the FFDRWG website.

## NWP BON Spillway rock mitigation – Marie Adams (PM), Adam Jones (TL), Jake Macdonald (FFDRWG)

Not currently on track for construction this Winter

Jeanette Wendler:  ROV spillway tailrace inspection completed 9/3/25. Results should be in by the end of Sept.

Erick Van Dyke: Will the results be shared with the group?

Jeanette Wendler: I will share at the next FPOM or next available time once I receive them.

## Bradford Island and Cascades Island LPS pump upgrades (Kovalchuk/White)

- Procuring equipment/supplies for construction this winter, BON Project will perform the work.

- Jeanette Wendler: Currently unfunded waiting for funding to compete work.

- Laurie Porter: How Confident are you that it will get funded?

- Jeanette Wendler: Unsure but will keep the group updated.

## NWP BON1 Ice & Trash PIT Detection – Mark Bierman (PM), Jeanette Flemmer (FFDRWG)

On track for installation as soon as Winter 2025-2026

Dave Swank: Has this been funded?

Gordy Axel: Request for bids was extended and closed last week. Hope to have selection by end of the month.

## NWP BON2 Submerged Traveling Screen (STS) Rehabilitation Phase 1a – Jeremy Nguyen (PM), Will Guest (TL), Jake Macdonald (FFDRWG)

PDT is developing alternatives to replace or rehab all 24 screens as well as procure one spare.  The original project was envisioned as a small cap effort. Due to previously executed work, there is a full drawing package and plans and specs that are near ready for advertisement. Therefore, the work envisioned in this project is to review the existing materials, update cost and schedule estimates, and proceed into construction.  One screen currently at Bonneville is from John Day and has a different construction.

Objectives:

  - Review existing project documentation to ensure consistency with observed condition and need.

  - Uniformity of devices and commonality of spare parts is a priority for the end user. During the Phase 1A the PDT will evaluate whether and how this objective can be achieved, as part of the overall alternatives analysis, with the intent of determining if interchangeability of parts is possible between all in service submerged traveling screens (inclusive of but not limited to STS in service at Bonneville and John Day). As the project proceeds the PDT will also determine an appropriate acquisition method for procurement.

  - Determine if replacement or rehabilitation is the most effective alternative.

  - Develop contract package for rehab or replacement of 24 STS depending on outcome of first objective.

  - Obtain one spare STS.

Some types of questions the PDT may ask in a future FFDRWG:

  - Any significant updates to STS design criteria since the FY16-FY17 timeframe?

  - Should we consider any changes to the STS design based on B2FGE evaluations in recent years?

  - Incorporate a brush or anti-foul coating to help prevent mussel accumulation in the future?

  - Will Guest 9/2- PDT is wrapping up the Phase 1 A alternatives district review this week for BON. More to report on at next month’s meeting.

Chris Magel: Is there talk of pursuing universal screens for flexibility of sharing between projects?

Karen Kelly: Yes, there has been talk, will discuss further during the review.

Dave Swank: Has there been issues with the STS regarding spacing and lamprey? The new designs need to consult the latest guidance for screen spacing. USFWS has new guidance.

Chuck Barnes: Have not had issues with the STS, the mesh is very small.

Karen Kelly: We will look at the guidance for screen criteria.

## NWP BON2 exit channel PIT detection for post-construction evaluation – Erin Kovalchuk (PM), Adam White (TL), Jake Macdonald (FFDRWG)

Preliminary results from the 2025 spring run will be available soon.  Final results from the 2025 passage season should be available by SRWG annual review in November.

## NWP BON2 junction pool lamprey trap/LPS - Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Project kicked off early FY25, however no significant design progress is expected the remainder of FY25.

Jeanette Wendler: Paused until FY26.

## NWP TDA North lamprey passage structure extension for volitional passage – Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Project kicked off early FY25, however no significant design progress is expected the remainder of FY25.

Eric Grosvenor: Paused until FY26.

## NWP JDA North lamprey passage structure extension for volitional passage – Courtney Hollins (PM), Nicholas Rillstone (TL), Jake Macdonald (FFDRWG)

Project kicked off early FY25, however no significant design progress is expected the remainder of FY25.

Paused until FY26.

## NWP JDA North lamprey passage structure water supply improvements – Erin Kovalchuk (PM), Stacy Jensen (TL), JDA Fisheries (FFDRWG)

Construction is complete and operating as intended.  Ready to remove from FFDRWG agenda.

Remove from agenda.

## NWP prototype floating adult lamprey collector for tribal translocation, aka. “FALCON” (*partner project; not a USACE design) – Ralph Lampman (TL), Jake Macdonald (FFDRWG)

Lab testing at Bonneville Hatchery through August 2025

In-river test at BON2 South downstream entrance area planned for Summer 2026

Laurie Porter: Testing in the hatchery is complete, plan to deploy into the river June of 2026.

## Chris Magel: Avian Predation in fish ladders (pelicans).

Will the pelican exclusion devices be used in 26?

How effective were the devices?

Laura Ricketts: Pelican Exclusion devices were installed in the South Ladder. Seemed to be very effective and plan to install again next year.

# NWW updates

## NWW IHR Turbine Cooling Water Exclusion - Karen Kelly (PM), Chuck Barnes (Bio)

- Continue evaluating using monthly strainer counts.

- ROV inspection in scroll case occurred 24 July. No issues found with exclusion device.

- Chuck will coordinate with Ops to plan for a test this winter to look at cooling water operation procedures when lamprey are present.

- Dave Swank: How does the cooling water intake function?

- Chuck Barnes: Cooling water continues to cycle when the unit is off, unless scroll case is dewatered for maintenance or the cooling water is shut off for other reasons. It is not currently standard operation to turn cooling water off when unit is off at Ice Harbor.

## NWW LLA Adult Ladder Turn Pool Gate - Greg Linklater (PM), Chuck Barnes (Bio)

- Scheduled for install next winter work window.

## NWW MNA Avian deterrence – Karen Kelly (PM), Ryan Ashcraft (Bio)

- Ryan Ashcraft: Thank you to those that provided comments. Response to comments will be addressed in Jacobs final report, due end of FY25.

- Charlie Morrill: Could you share comments others had on the report?

- Ryan Ashcraft: Yes, we should be able to get those posted to the website.

## NWW MNA PIT Detection – Kat Herzog (PM), Chuck Barnes (Bio)

- Finalizing USACE EDR effort, plan to go to design phase in FY26. EDR will be sent to FFDRWG for review in September.

- Erick Van Dyke: Is embedded TSW option still an option?

- Chuck Barnes: The Matrix design will be the recommended plan in the report, but no design has been ruled out. Problem with the embedded TSW is we would be constricted to bay 22 and would need to construct in a way the antennas wouldn’t getting crushed when closing the TSW.

- Erick Van Dyke: TSW is the design that we the region think has potential. We think this concept should continue in the design phase.

- Chuck Barnes: Early next FY I’d like to have a meeting to discuss the alternatives ideas and potential constraints.

- Charlie Morrill: Has the debris, access, and maintenance of the matrix been discussed?

- Chuck Barnes: More detailed conversations will take place during the design phase.

## NWW John Day Dam and Snake River Ladder Cooling – Karen Kelly (PM), Ryan Laughery (TL), Ryan Ashcraft (FFDRWG)

- Ryan Ashcraft: Thank you to those that provided comments. Response to comments will be addressed in Jacobs final report, due end of FY25.

- Erick Van Dyke: Will there be a priority project or will all the projects be done at the same time?

- Karen Kelly: There will be a prioritization of the projects.

- Erick Van Dyke: Appreciate the combination of projects on this effort.

## NWW MNA Turbine Replacement – Jean DesJarlais (PM), Jon Renholds (TL)

- Finalized F3 Design in late August at ERDC. Results of final F3 Design will be presented at October FFDRWG.

# Upcoming meetings and field trips

## Fish Facilities Design Review Work Group (FFDRWG) = first Thursday of every month (contact Jake Macdonald and Chuck Barnes if you need an invitation).

### Thursday 10/2/25 @ 09:00

## Fish Passage Operation & Maintenance (FPOM) Work Group = second Thursday of every month = (contact Patricia Madson and Chris Peery if you need an invitation).

### Thursday 9/11/25 @ 09:00 and Thursday 10/9/25 @ 09:00

## Studies Review Work Group (SRWG) FY 2026 Planning Cycle: https://public.crohms.org/tmt/documents/FPOM/2010/SRWG/FY26AFEPplanning/

### FY26 SRWG final proposal review meeting – Thursday 9/18/25 at 1230 after the SCT meeting.  Location: In-Person @ TBD Portland Location

## Upcoming Field Trips: