## FY26 Ranking Sheet
CRFM FY26 RANKING SPREADSHEET
FY26 PBud: $30.05M
FY26 Original capability: $144M -- will be updated to reflect FY25 budget and available resources
FY26 Final Workplan: TBD
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY25 Scope) | FY26 PBud | Mandatory or S&A Item | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | CORPS Score | BPA Score | SCT Average Score | USACE notes | Agency Remarks
Willamette
1 | Willamette |  |  |  | Total - Willamette (NWP) | 18050
Lamprey
2 | Various CRS | Continue efforts on lamprey work contemplated in the Columbia River Basin Fish Accords |  |  | Total - Lamprey (NWW/NWP)*
CRS
|  | **Means co-funded with BPA |  |  | Total - CRS (NWW/NWP) | 12000
3 | SYS | Post Construction Performance Standard Evaluations** | Royer | 156117 | Lower Columbia/estuary PIT trawl - contract in FY26 is for prep and field work the summer 2027 | 1000
Recovery of PIT tags from ESI bird colony to support LCR survival estimates and avian predation rate estimates as appropriate - in house labor
4 | SYS | Avian Island PIT Detection | Simon | 395290 | Avian predation rate estimates - utilizing existing data | 0
6 | SYS | CRS Spill Evaluations | Royer | 515375 | Evaluate impacts of spill operations on migrating salmonids | 0
8 | SYS | CRS Environmental Compliance | Reese | 567831 | Complete legal compliance for new system operations. | Not budgeted | M
9 | SYS | NWD Program Management | NWD |  | Internal and external program coordination |  | M
10 | SYS | CRS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support |  | M
11 | EST | Estuary Habitat Studies | Bierman | 123452 | Estuary habitat studies - Acoustic monitoring year 2 (dependent on availability of AT fish upriver) | 0
Estuary habitat studies - SAV characterization, Prey enegy density library
14 | BON | Bonneville PIT Detection** | Bierman | 478299 | Installation of BPA-funded PIT antenna prototype at BON1 Ice and Trash Sluiceway; assumes contract award FY25 | Not budgeted
16 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Adams | 142630 | Continue design and construction contract award for a debris removal alternative for the auxiliary water supply intake. | Not budgeted
17 | JDA | JDA ladder cooling | Kelly | 515374 | Continue design for an alternative to cool water in the John Day Dam adult fish ladder. | 0
18 | JDA | John Day Mitigation | Clemente | 515590 | Planning study (alternatives analysis), year 3 | 0
19 | JDA | John Day Fish Turbine Pumps U1 & U2 | Ernster | 520639 | Continue design for the John Day Dam south fish turbines. This is for a long-term solution. (Short-term project is O&M funded.) | Not budgeted
20 | SYS | CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. |  | M
21 | MCN | MCN Adult Ladder (south) Cooling Structure | Kelly | 516493 | Continue design for an alternative to cool water in the south adult fish ladder at McNary Dam. | 3000
22 | MCN | MCN Avian Deterrence | Kelly | 517408 | Continue design for an avian predation deterrance alternative at McNary Dam | 0
23 | MCN | MCN PIT Detection Improvements | Herzog | 518186 | Continue design for a PIT detection altenative at McNary Dam | 4000
24 | MCN | MCN Spillway Modeling | Kelly | 515316 | Conduct EDRC modeling of McNary spillway to maximize operation for fish passage. | 0
25 | MCN | MCN Fish Pump System Upgrade | Francis | 568570 | Continue design for rehabilitation of the McNary Dam fish turbines | Not budgeted
26 | MCN | MCN South Fish Ladder and Collection Channel Rehab |  |  | Continue design for rehabilitation of the McNary Dam south fish ladder and collection channel | Not budgeted
28 | IHR | IHR Adult Ladder (north) Cooling Structure | Kelly | 517666 | Continue design (EDR, DDR) for ladder cooling structure at the IHR north fish ladder. | 0
| IHR | IHR Turbine Post-Construction Evaluation |  |  | Initiate scoping effort for future study to evaluate effectiveness of new IHR turbines on fish passage and survival | Not budgeted
29 | LMN | LMN Adult Ladder (south) Cooling Structure | Kelly | 516906 | Continue design (EDR, DDR) of ladder water cooling structure | 4000
30 | LMN | LMN Adult Channel and North Entrance Diffuser Grating | Robison | 568912 | Initiate design of new diffuser grating at the LMN north fish ladder entrance and adult channel | Not budgeted
32 | LGR | Lower Granite Turn Pool Gate | Linklater | 372529 | FY26 funding is for installation the winter of 2025-26. | Not budgeted
33 | LGR | Lower Granite Shad Deterrence | Kelly | 566948 | FY26 funding for scoping and preliminary testing. | Not budgeted

## FY25 Ranking Sheet
CRFM FY25 RANKING SPREADSHEET
Assumption is that these scores are for FY25 funding
|  | FY25 Final Workplan $38.98M |  |  | Corps scoring criteria: Construction highest priority, projects with a timeline
|  | FY25 Carry-in from FY24: $27.5M |  |  | Research with a date completion date associated with the requirement a higher priority
FY25 Total funding: $63.5M
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY25 Scope) | FY25 PBud [$75.2M] | FY25 Final Workplan [$39M] | FY25 Budget [63.5M] | Mandatory or S&A Item | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | CORPS Score | BPA Score | SCT Average Score | USACE notes | Agency Remarks - 20 March 2025
Willamette
1 | Willamette |  |  |  | Total - Willamette (NWP) | 50550 | 19034 | 36409
Lamprey
2 | Various CRS | Continue efforts on lamprey work contemplated in the Columbia River Basin Fish Accords |  |  | Total - Lamprey (NWW/NWP)* | 5,000 | 4300 | 5713
CRS
|  | **Means co-funded with BPA |  |  | Total - CRS (NWW/NWP) | 19650 | 12650 | 21478 |  |  |  | * Means - Conditions
3 | SYS | Post Construction Performance Standard Evaluations** | Royer | 156117 | Lower Columbia/estuary PIT trawl - contract in FY25 is for prep and field work the summer 2026 | 1500 | 1500 | 1200 |  |  |  | 5 |  | 5 |  | 5 | 5 |  | 5 | 5 | 5 | Importance for survival estimates
4 | SYS | Avian Island PIT Detection | Simon | 395290 | Recovery of PIT tags from ESI bird colony to support LCR survival estimates and avian predation rate estimates as appropriate - in house labor | 150 | 150 | 50 |  |  |  | 5 |  | 4 |  | 4 | 4 |  | 4 | 4 | 4.1667
|  | ESI Predation Rate Estimate |  |  | Analysis and reporting of PIT tag information to generate predation estimates - research contract | [6 empty] | 4 |  | 4 |  | 4 | 4 |  | 2 | 1 | 3.1667 | Predation analysis not required every year | YN: We're discussing management efforts in the next year or two; without the analysis and reporting the data isn't useful. Near-term, predator management is important. CTUIR: There's been a couple years when we haven't done the analysis, there's some concern that travel restrictions wouldn't allow other work in estuary. This could be a critical year to determine what the impact of that would be. Wants data to indicate what the predation impacts are. IDFW: Given the number of birds on ESI in last few years, don't see a need to do that at ESI; feels the need to do this more for the whole estuary. There is a limitation on the scope of this since it's just for ESI. However, if folks can't travel then the funding could be used for analysis and reporting. ODFW: Reference legal documents for what is/isn't required.
|  | Avian Predation Monitoring | Clemente | 152054 | Working real estate actions to transfer ownership of avian island areas in order to close out this project |  |  | 35
5 | SYS | CRS Fish Asset Condition Scoping | Royer |  | Evaluate existing fish assets and determine what repairs are needed; assessment will determine appropriate account for budgeting |  |  | 0 |  |  |  | 5 |  | 5 |  | 5 | 5 |  | 1 | 1 | 3.6667 | Army Corps will pursue this information via their O&M processes. | IDFW: Ranked high. The normal process has led us to where we are now, we need a concerted effort to address these projects. YN: We have a backlog of work, the #1 priority is maintaining the equipment we have in place. We can't meet the BiOp standards with the current condition of equipment. We need the information and evidence to lobby and get the funding to get the equipment to perform. Assumption is that if we do the scoping it will be more transparent about what it takes to maintain the assets. CTUIR: Concerned that if it's given a low score the funding would disappear. ODFW: This is not new, equipment has been deteriorating for decades. High priority in order to recommend actions. NOAA: Agrees with region on this. If we were presented with a reasonable pathway that we're using to address these issues could agree with the Corps. We're starting to see substantial effects of infrastructure impacting passage criteria, spill priority lists. Thought this would be a process where we could deal with this. WDFW: Agrees with everything heard. BPA: This line item is separate from the Fish Assets and their importance. There is a process internal to the Corps for tracking assets. There is a difference between identifying these things vs. having a concern for the backlog. This line item won't change how we view the relative importance of the assets.
6 | SYS | CRS Spill Evaluations | Royer | 515375 | Evaluate impacts of spill operations on migrating salmonids | 5500 | 500 | 5850 |  |  |  | 4 |  | 3 |  | 4 | 5 |  | 5 | 5 | 4.3333 | In Proposed Action and RCBA Requirement to do study in 2025. Already awarded. | YN: Maintaining our long-term datasets with PIT detection is their highest priority, the AT study is lower priority.
7 | SYS | Columbia River System Operations | NWD | 469690 | Resolution of contract dispute; final payout |  |  | 87 | M |  |  | M |  |  |  |  | D
8 | SYS | CRS Environmental Compliance | Reese | 567831 | Complete legal compliance for new system operations |  |  | 7000 | M |  |  | M |  | 5 |  |  | D |  |  |  | 5 | Required to complete fish passage actions | CTUIR: The highest cost item on this sheet is a NEPA line item.
9 | SYS | NWD Program Management | NWD |  | Internal and external program coordination |  |  | 180 | M |  |  | M |  |  |  | 2 | 3 |  |  |  | 2.5
10 | SYS | CRS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support |  |  | 600 | M |  |  | M |  |  |  | 3 | 3 |  |  |  | 3
11 | EST | Estuary Habitat Studies | Bierman | 123452 | Acoustic telemetry study and prey flux study - awarded early FY25 | 850 | 850 | 650 |  | 2 |  | M |  |  |  | 2 | 4 |  | 3 | 2 | 2.6 | Already awarded
4
12 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Smith | 122645 | Project closeout | 100 | 100 | 10 | M |  |  | M |  |  |  |  | D
13 | BON | BON Powerhouse 2 post-construction evaluation | Royer | 515346 | Post-construction evaluation of the replacement of the flow restrictor plates in the PH2 gatewells, year 2 of 2 | 500 | 500 | 60 |  |  |  | M |  | 3 |  |  | D |  | 0 | 0 | 1 | For the 2025 study, concern over confounding spill eval
14 | BON | Bonneville PIT Detection** | Bierman | 478299 | Installation of BPA-funded PIT antenna prototype at BON1 Ice and Trash Sluiceway auto-gate |  |  | 350 |  |  |  | 4 |  | 5 |  | 5 | 5 |  | 4 | 5 | 4.6667 | Install this year; tied to system survival eval | BPA will try to keep us updated on contracting status
15 | BON | BON Serpentine Weir Modifications | Kovalchuk | 519996 | Construction oversight - fully funded in FY24 |  |  | 1750 | M |  |  | M |  |  |  |  | M
16 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Adams | 142630 | Continue design for debris removal alternative for auxiliary water supply intake | 1250 | 1250 | 250 |  |  |  | 4 |  | 4 |  | 3 | 4 |  | 5 | 5 | 4.1667 | Direct survival benefits | CTUIR - Also providing comments on the design document. Since timeline for the turbines is so far out, that's why a lower score. NOAA - Some conern that if not funded in present day, it won't have funding later.
17 | JDA | JDA ladder cooling | Kelly | 515374 | Ladder cooling analysis, DDR/P&S | 600 | 600 | 80 |  | 3 |  | 5 |  | 5 |  | 5 | 5 |  | 4 | 3 | 4.2857 |  | NOAA - Feels these are important because in some years there is a direct survival impact. Clearly described in Proposed Action / BiOp. IDFG - In a limited funding environment, would prioritize LoMo over JDA.
18 | JDA | John Day Mitigation Report | Clemente | 515590 | Planning study (alternatives analysis), year 2 | 1000 | 1000 | 1100 |  | 2 |  |  |  | 5 |  | 4 | 3 |  | 2 | 2 | 3 |  | IDFG, YN - Does not seem to belong in CRFM
19 | JDA | John Day Fish Turbine Pumps U1 & U2 | Ernster | 520639 | Long-term solution for the JDA south ladder fish turbines; FY25 initiating design |  |  | 200 |  |  |  | 5 |  | 3 |  | 5 | 5 |  | 5 | 5 | 4.6667
20 | SYS | CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. |  |  | 30 | M |  |  | M |  |  |  |  | D
21 | MCN | MCN Adult Ladder (south) Cooling Structure | Kelly | 516493 | Continue design process for a ladder cooling structure at the MCN south fish ladder | 500 |  | 100 |  |  |  | 5 |  | 4 |  | 4 | 5 |  | 4 | 3 | 4.1667
22 | MCN | MCN Avian Deterrence |  | 517408 | Construction contract award of avian predation deterrent system | 5000 | 5000 | 100 |  |  |  | 5 |  | 4 |  | 5 | 5 |  | 4 | 4 | 4.5 | Does not address many bird predation concerns; would rank lower than other '4' scores.
23 | MCN | MCN PIT Detection Improvements |  | 518186 | Continue design for PIT detection improvements (EDR, DDR) | 600 | 600 | 190 |  |  |  | 5 |  | 5 |  | 5 | 5 |  | 5 | 5 | 5 | Needed for survival estimates
24 | MCN | MCN Spillway Modeling |  | 515316 | Conduct EDRC modeling of McNary spillway to maximize operation for fish passage. | 2000 |  | 900 |  | 5 |  | 5 |  | 5 |  | 3 | 3 |  | 4 | 3 | 4 | Already construction and used once; potentially another trip this year | IDFG - If the Corps would use a lack of modeling to justify decisions then would rank this a 5. Important if it allows the Corps enough comfort level to open Bay 18.
25 | MCN | MCN Fish Pump System Upgrade |  | 568570 | Initiate design for rehabilitation of the McNary Dam fish turbines |  |  | 150 |  | 4 |  | 4 |  | 4 |  | 5 | 4 |  | 5 | 5 | 4.4286
26 | MCN | MCN South Fish Ladder and Collection Channel Rehab |  |  | Initiate design for rehabilitation of the McNary Dam south fish ladder and collection channel |  |  | 0 |  |  |  | 4 |  | 4 |  | 4 | 4 |  | 5 | 5 | 4.3333 | Tied to fish pump rehab; pump discharges into channel and ladder (valves, conduit, etc.)
27 | IHR | Ice Harbor Turbine Passage Survival Program | Walker | 334588 | Completion and project closeout |  |  | 19 | M |  |  | M |  |  |  |  | D
28 | IHR | IHR Adult Ladder (north) Cooling Structure | Kelly | 517666 | Continue design (EDR, DDR) for ladder cooling structure at the IHR north fish ladder. |  |  | 130 |  | 3 |  | 5 |  | 5 |  | 5 | 5 |  | 4 | 4 | 4.4286
29 | LMN | LMN Adult Ladder (south) Cooling Structure | Kelly | 516906 | Continue design (EDR, DDR) of ladder water cooling structure | 600 | 600 | 120 |  | 5 |  | 5 |  | 5 |  | 5 | 5 |  | 4 | 4 | 4.7143 |  | IDFG - Blockage tied to temps at LMN is visually apparent. NOAA - Believes blockage is visually apparent at all locations. Agrees that some are higher priority.
30 | LMN | LMN Adult Channel and North Entrance Diffuser Grating |  | 568912 | Initiate design of new diffuser grating at the LMN north fish ladder entrance and adult channel |  |  | 50 |  |  |  | 3 |  | 4 |  | 3 | 3 |  | 5 | 5 | 3.8333
31 | LGO | Little Goose Adult Ladder Temperature Mitigation - Fish egress project |  | 456609 | Construction to allow fish egress out of cooling structure. Closeout. |  |  | 120 | M |  |  | M |  | 4 |  |  | D |  |  |  | 4
32 | LGR | Lower Granite Turn Pool Gate |  | 372529 | FY25 to complete construction, automating hoist system to make more usable and improve fish egress in ladder. |  |  | 40 |  | 3 |  | 3 |  | 4 |  | 4 | 4 |  | 5 | 5 | 4 | Mid-construction, will finish next year | IDFG - Wondering if their info on walleye is influencing the design. Corps - Will discuss at next FFDRWG.
33 | LGR | Lower Granite Shad Deterrence |  | 566948 | FY25 funding for scoping and preliminary testing. |  |  | 21 |  | 2 |  | 3 |  | 3 |  | 3 | 3 |  | 5 | 4 | 3.2857 | Direct passage benefit | IDFG - Wouldn't characterize this as a direct passage benefit. NOAA - Would like to get it, but don't think it's been identified as a passage issue. Lower in priority.
34 | LGR | Lower Granite Juvenile Bypass Facility |  | 493013 | Project closeout |  |  | 56 | M | [7 empty] | M |  |  |  | #DIV/0!
Note on R23: Trevor Conder: Needs Discussion
Note on R28: Trevor Conder: Needs discussion for NOAA rank

## FY24 Ranking Sheet
CRFM FY24 RANKING SPREADSHEET
17 JUN 2024
FY24 Final Workplan: $66.67M
FY24 Carry-in: $22.8M
--- $7.4M Lamprey
--- $14.3M Willamette
--- $1.0M CRS
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY24 Scope) | FY24 PBud | FY24 Planned Allocation [07 JUN 2024] | Mandatory or S&A Item | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | CORPS Score | BPA Score | SCT Average Score | USACE notes | Agency Remarks During Ranking
Willamette
1 | Willamette |  |  |  | Total - Willamette (NWP) | 42850 | 33083
Lamprey
2 | Mult. CRS |  |  |  | Total - Lamprey (NWW/NWP) | - | 6100
FCRPS
|  | **Means co-funded with BPA |  |  | Total - CRS (NWW/NWP) | 23820 | 27487 |  |  |  | * Means - Conditions
3 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight - for a contract in FY24 for prep and field work summer 2025. | 1500 | 1285 |  | 5 |  | M |  | 5 |  | 5 | 5 |  | 5 | 5
4 | SYS | Avian Island PIT Detection** | Simon | 395290 | Recovery of PIT tags from ESI bird colony to support LCR survival estimates and avian predation rate estimates as appropriate - in house labor | 200 | 170 |  | 5 |  | 5 |  | 5 |  | 5 | 5 |  | 4 | 4
|  | ESI Predation Rate Estimate |  |  | Analysis and reporting of PIT tag information to generate predation estimates - research contract |  |  |  | 2 |  | 4 |  | 5 |  | 4 | 3 |  | 3 | 3
5 | SYS | Inland Avian Predation | Kelly | 328188 | Blalock Island - FY24 scope to complete reporting and for NWW coordination | 50 | 5 |  |  |  | 2 |  | 3 |  | 2 | 4 |  | 3 | D |  | FY24 scope to continue coordination and incorporate additional information | NOAA and WDFW: Feel more work to be done in regional avian presence.
| SYS | Avian Predation Monitoring | Robledo | 152054 | Complete real estate transaction to tranfer ownership of constructed islands
6 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Closing out old contracts - contract dispute finalized |  | 75
7 | SYS | FCRPS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support | 0 | 400 | M
8 | SYS | CRS RM&E Spill Evaluation | Budai | 515375 | Evaluate impacts of the spill operation on migrating salmonids | 400 | 4000 |  | 3 |  | 5* |  | 3 |  | 3 | 5 |  | 5 | 5 |  |  | WDFW condition: Not sure where the study is going.
9 | ESTU | Estuary Habitat Studies | Bierman | 123452 | Data transparency and web interface | 620 | 160 |  | 1 |  | 2 |  | 4 |  | 3 | 3 |  | 3 | 3
[5 empty] | Estuary habitat uncertainties | [5 empty] | 4 |  | 4 |  | 2 | 4 |  | 3 | 3
10 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Smith | 122645 | FY24: Contract oversight EDC/S&A in remaining units (construction CT funded FY21), PDT labor | 400 | 400 | M | 4 |  | M |  | 4 |  | 3 | M |  | M | M
11 | BON | BON Powerhouse 2 post-construction evaluation | Budai | 515346 | Post-construction evaluation of the replacement of the flow restrictor plates in the PH2 gatewells. | 450 | 600 |  | 4 |  | 5 |  |  |  | 4 | 5 |  | 5 | 5
12 | BON | Bonneville PIT Detection** | Kovalchuk | 478299 | Installation of BPA-funded PIT antenna prototype at BON1 Ice and Trash Sluiceway auto-gate | 300 | 305 |  | 3 |  | 5* |  | 5 |  | 3* | 3 |  | 3 | 4 |  |  | WDFW Condition: Not sure of the level of support for use.
13 | BON | BON Serpentine Weir Modifications | Kovalchuk | 376133 | Complete P&S and award construction contract | 10000 | 10000 |  | 2 |  | 1 |  | 4 |  | 5 | 1 |  | 5 | 5 |  |  | NOAA: Lamprey should fund this, benefit to salmonids is minimal to negative. Full construction should not be from "salmon" portion.
14 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Kovalchuk | 142630 | Continued design - FY24 funding supports a design contract for completing DDR/P&S | 4200 | 1000 |  | 4 |  | 4 |  | 4 |  | 4* | 4 |  | 5 | 5
15 | JDA | JDA ladder cooling | Rerecich | 515374 | Initiate design to evaluate structural ladder cooling alternatives. Award contract for altneratives analysis (EDR) in FY24. | 500 | 500 |  | 4 |  | 3 |  | 5 |  | 5 | 4 |  | 4 | 3
16 | JDA | John Day Mitigation | Cook | 122434 | Initiate a new Planning study (alternatives analysis) to include Umatilla Hatchery as an alternative. | 1000 | 500 |  | Defer to downriver interests |  | M |  | 5 |  | 4 | 3 |  | 4 | 4
17 | SYS | FCRPS CRFM Program Management (NWW) | Sipe | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. | 0 | 115 | M
18 | MCN | MCN Adult Ladder (south) Cooling Structure | Zelch | 516493 | Initiate design process for a ladder cooling structure at the MCN south fish ladder. Award contract for altneratives analysis (EDR) in FY24. | 500 | 600 |  | 4 |  | 3 |  | 5 |  | 5 | 4 |  | 4 | 3
19 | MCN | MCN Avian Deterrence |  | 517408 | Initiate design efforts for predation deterrence at MCN | 600 | 600 |  | 4 |  | 4 |  | 5 |  | 5 | 4 |  | 4 | 4
20 | MCN | MCN PIT Detection Improvements |  | 518186 | Initiate an EDR to evaluate PIT detection alternatives at MCN | 500 | 500 |  | 5 |  | 5 |  |  |  | 5 | 5 |  | 3 | 4
21 | MCN | MCN Spillway Modeling |  | 515316 | Conduct EDRC modeling of McNary spillway in FY24. Biological studies conducted utilizing balloon tags and acoustic telemetry. | 1500 | 4421
22 | IHR | Ice Harbor Turbine Passage Survival Program | Walker | 334588 | Contract oversight, labor. Completion in FY24. Delays in schedule resulted in need for contract modification. | 0 | 230 | M | 1 |  | M |  | 5 |  |  | M |  | M | M |  |  | IDFG: Using the 2008 scoring criteria, this project has a relatively low expected survival improvement (most fish go through spillways), therefore recieves low priority.
23 | IHR | IHR Adult Ladder (north) Cooling Structure | Zelch | 517666 | Initiate design of new ladder cooling structure at the ICH north fish ladder. Award contract for altneratives analysis (EDR) in FY24. | 0 | 500 |  | 4 | [5 empty] | 5 | 4 |  | 3 | 2 |  | Lower score to prioritize other projects. | NOAA: If there's a way to include IHR in project scope for other ladder cooling efforts, would be more efficient and complete this project completed sooner. Higher priority than serpentine weir. Also, better options than the LGR design so should look at more options.
24 | LMN | LMN Adult Ladder (south) Cooling Structure | Zelch | 516906 | Initiate design process for a ladder cooling structure at the LMN south fish ladder. Award contract for altneratives analysis (EDR) in FY24. | 500 | 500 |  | 5 |  | 3 |  | 5 |  | 4 | 4 |  | 4 | 3
25 | LGO | Little Goose Adult Ladder Temperature Mitigation - Fish egress project |  | 456609 | FY24 to complete design and initiate fabrication to allow fish egress out of cooling structure. | 250 | 250 |  | 4 |  | 4 |  | 5 |  | 4 | 4 |  | 3 | 3
26 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) | Martin | 372857 & 493013 | Project closeout in FY24 | 0 | --- | M | 5 |  | M |  | 5 |  |  | M |  | M | M
27 | LGR | Lower Granite Turn Pool Gate |  | 372529 | Shad deterrence, automating hoist system to make more usable and improve fish egress in ladder. FY24 construction. | 250 | 331 |  | 3 |  | 4 |  | 5 |  | 4* | 5 |  | 4 | 4
| SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget
| SYS | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder - not currently in budget) | [5 empty] | 5
| TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget
| LGO | Little Goose Adult Ladder PIT Feasibility (Placeholder) | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 (Placeholder - not currently in budget)
| LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings (Placeholder) | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW (Placeholder - not currently in budget)
5
Note on H25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Utilizing carry-in funds for contract actions.

## FY23 Ranking Sheet
CRFM FY23 Ranking Sheet (11 OCT 2023)
FY23 PBud: $29.175M
FY23 Final Work Plan: $47.4M
Total Carry-in: $71.5M
--- $15.5M Lamprey
--- $53.9M Willamette
--- $2.1M CRS
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY23 Scope) | FY23 Final Work Plan | FY23 Execution | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT Average Score | USACE notes | Agency Remarks During Ranking | Agency Remarks during 8/18/21 SCT meeting
Willamette
1 | Willamette |  |  |  | Total - Willamette (NWP) | 43150 | 82119 | Y | [11 empty] | M
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP)* | - | 8254 | Y | [11 empty] | M
FCRPS
|  | **Means co-funded with BPA |  |  | Total - CRS (NWW/NWP) | 4250 | 5478
3 | SYS | Lower Columbia River Juvenile Survival Studies** | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight - for a contract summer 2023 for prep and field work summer 2024. (Field work 2023 funded FY22.) | 1200 | 2386 | N | 5 | 5 | 5 |  | 5 |  | 5 | 5 |  | 5 | 5 | 5 | Performance evaluation of increased spill | Fish manager consensus: Should be a mandatory item because it's a basic part of monitoring. Basic part of AM in the basin. | USACE: Used to evaluate flex spill operation.
4 | SYS | Avian Island PIT Detection** | TBD | 395290 | Recovery of PIT tags from ESI bird colony to support LCR survival estimates and avian predation rate estimates as appropriate - in house labor | 20 | 12 | N | 5 | 5 | 5 |  | 5 |  | 5 | 5 |  | 4 | 4 | 4.75 |  | Note: Part of the Proposed Action, commitment was to reassess synthesis report. NOAA: There is expanded value to this activity.
|  | ESI Predation Rate Estimate |  |  | Analysis and reporting of PIT tag information to generate predation estimates - research contract |  |  | N | 3 |  | 3 |  |  |  | 3 |  |  | 3 | 2 | 2.8 | Predation analysis isn't required every year |  | CRITFC: Lower score this year, but does believe having a check-in is important. USACE: We can do retroactive analysis. IDFG: Is it more efficient to fund every few years.
5 | SYS | Inland Avian Predation | Kelly | 328188 | Blalock Island - Reservoir operations/monitoring, year 3. | 10 | 12 | N | 2 | D | 3 |  | 3 |  | 1 | 4 |  | 3 | 3 | 2.7143
6 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Litigation expenses | 0 | 0 | M | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | M | 0 |  | CTUIR: Strongly recommend the Corps not to utilize CRFM for litigation. General fish manager consensus: CRFM should not be used for litigation. | Regional fish managers: Litigation expenses shouldn't be funded from mitigation funds.
7 | SYS | FCRPS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support | 350 | 465 | M |  |  |  |  | N/A | [5 empty] | M |  |  | OR: Budget shortfalls should generate consideration of restructuring.
8 | SYS | FCRPS CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. | 50 | 0 | M |  |  |  |  | N/A | [5 empty] | M
9 | SYS | Avian Predation Monitoring | Robledo | 152054 | Complete real estate transaction to tranfer ownership of constructed islands | 50 | 7 | N
10 | ESTU | Estuary Habitat Studies | Bierman | 123452 | Synthesis Memo #3, CEERP coordination | 500 | 341 | N | 3 | 2 | 2 |  | 2 |  | 2 | 5 |  | D | 3 | 2.7143 |  | NOAA: Willing to meet with USACE to determine if the scope could be modified to reduce cost.
11 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Adams | 122645 | Contract oversight EDC/S&A in remaining 7 units (construction CT funded FY21), PDT labor | 600 | 723 | M | 2 | 2 | 3 |  | N/A |  | 2 | 4 |  | 5 | M | 3
12 | BON | Bonneville PIT Detection** | TBD | 478299 | Design review of BPA-funded PIT antenna prototype at BON1 Ice and Trash Sluiceway auto-gate | 90 | 100 | N | 5 | 5 | 5 |  | 5 |  | 5 | 5 |  | 5 | 3 | 4.75
13 | BON | BON Serpentine Weir Modifications | Woodard | 376133 | Cost share with lamprey. FY23 design only / construction FY24. | 200 | 72 | N | D | 2 | 2 |  | 3 |  | D | D |  | 4 | 4 | 3
14 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Kovalchuk | 142630 | Engineering Design Report - develop preferred alternative for debris management in FY23 | 200 | 449 | N | 4 | 3 | 3 |  | 3 |  | 4 | 4 |  | 4 | 5 | 3.75
15 | JDA | John Day Mitigation | Chane | 122434 | Analysis for JDA - Limited Reevaluation Report / Umatilla Hatchery | 200 | 4 | N | D | 2 | D |  | 4 |  | 4 | 3 |  | D | 1 | 2.8
16 | ICH | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Contract oversight, labor | 120 | 235 | M | 1 | 1 | 1 |  | N/A |  | N/A | N/A |  | 5 | M | 2 |  | IDFG: Corps previously stated that if most fish are passing through spill, why look at turbines
17 | LGO | Little Goose Adult Ladder Temperature Mitigation | Juhnke | 456609 | Added new Work Item for Cooling Intake Sluice Gate - sluice gate to allow fish to egress out of cooling structure. | 50 | 76 | N | 4 | D | D |  | 4 |  | 3 | 4 |  | 4 | 3 | 3.6667
18 | LGR | Lower Granite Juvenile Bypass Facility | Martin | 372857 & 493013 | Funding for contract oversight, labor in FY23. | 500 | 512 | M | 3 |  | N/A |  | N/A |  | 3 |  |  |  |  | 3
19 | LGR | Lower Granite Turn Pool Gate |  | 372529 | Shad deterrence, automating hoist system to make more usable and improve fish egress in ladder | 50 | 79 | N | 3 | 3 | 3 |  | 3 |  | 3 | 3 |  | 3 | 4 | 3.125
| SYS | FUTURE: CRS RM&E Flex Spill Evaluation |  |  | Evaluate impacts of the flex spill operation on migrating salmonids.
| BON | FUTURE: BON Powerhouse 2 post-construction evaluation |  |  | Post-construction evaluation of the replacement of the flow restrictor plates in the PH2 gatewells.
| JDA | FUTURE: JDA ladder cooling | TBD | TBD | Conduct an EDR to evaluate structural ladder cooling alternatives | - |  | N | 4 | 4 | 4 |  |  |  | 5 | 5 |  | 3 | 4 | 4.1429 |  | Revisit in August for scoring. Clarify scope/description. | Prioritization among ladder cooling projects will occur in another forum/meeting.
| MCN | FUTURE: MCN Adult Ladder (south) Cooling Structure | TBD | TBD | Design and contruction of a new ladder cooling structure at the MCN south fish ladder | - |  | N | 4 | 4 | 4 |  | 4 |  | 5 | 5 |  | 3 | 4 | 4.125 |  | Regional fish managers: relative differences among ladder cooling is indicative of preference of order; all are important. | Prioritization among ladder cooling projects will occur in another forum/meeting.
| MCN | FUTURE: MCN Avian Deterrence | TBD | TBD | Funding to complete EDR/Design effort leading to construction of predation deterrence | - |  | N | 4 | D | 5 |  |  |  | 5 |  |  | 3 | 4 | 4.2 |  | Revisit in August
| MCN | FUTURE: MCN PIT Detection Improvements |  |  | Conduct an EDR to evaluate options to improve PIT detections at MCN
| ICH | FUTURE: ICH Adult Ladder (north) Cooling Structure | TBD | TBD | Design and contruction of a new ladder cooling structure at the ICH north fish ladder | - |  | N | 4 | D | 4 |  | 4.5 |  | 4 | 4 |  | 3 | 4 | 3.9286 | USACE would prioritize this project behind others | Regional fish managers: relative differences among ladder cooling is indicative of preference of order; all are important. | Prioritization among ladder cooling projects will occur in another forum/meeting.
| LMN | FUTURE: LMN Adult Ladder (south) Cooling Structure | TBD | TBD | Design and contruction of a new ladder cooling structure at the LMN south fish ladder | - |  | N | 5 | D | 4 |  | 5 |  | 5 | 5 |  | 3 | 4 | 4.4286 |  | Regional fish managers: relative differences among ladder cooling is indicative of preference of order; all are important. | Prioritization among ladder cooling projects will occur in another forum/meeting.
| Lamprey CRFM | FUTURE: Lamprey - BON Serpentine Weir and other lamprey passage improvements
20 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | - | [8 empty] | D |  |  | D | D
22 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder - not currently in budget) | - |  |  | 5 | 5 | 4 |  |  |  | 4 |  |  | D | D | 4.5
21 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | - |  |  | 5 | 5 | 5 |  |  |  | 5 |  |  | D | D | 5
23 | LGO | Little Goose Adult Ladder PIT Feasibility (Placeholder) | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 (Placeholder - not currently in budget) | - |  |  | 5 | 5 | 5 |  |  |  | 3 |  |  | D | D | 4.5
24 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings (Placeholder) | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW (Placeholder - not currently in budget) | - |  |  |  |  | D |  |  |  | D |  |  | D | D
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $1.3M of carry-in awarded in Q1 for 2023 field work.
Note on H32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $125k of carry-in
Note on H34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $263k of carry-in

## FY22 Ranking Sheet-Sept
CRFM FY21 RANKING SPREADSHEET |  |  | Updated By: I. Royer |  | 2021-09-13
|  | FY22PBud $3.575 M | FY21 Lamprey $19.937
FY22 Senate mark-up: $34.8M
FY22 Final budget: TBD
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY21 Scope) | FY22 Capability (in thousands) | FY22 Pbud (in thousands) | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2021 Average Score | Agency Remarks During Ranking | Agency Remarks during 8/19/21 SCT meeting
Willamette
1 | Willamette |  |  |  | Total - Willamette (NWP) | 34800 | 2000 | Y | [11 empty] | M
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP)* | - | - | Y | [11 empty] | M
FCRPS
[5 empty] | Total - CRS (NWW/NWP) | 6310 | 1575 | [8 empty] | (General): These ranks are lower than typical because of the need to add ranking contrast with the possiblity of a low funding year. A low rank does not necessarily indicate a lack of NOAA support, but rather indicates how we would prioritize funding in 2022 given it could be low. If funding is below or above expectations, we may consider re ranking accordingly. Some projects are important but could be pushed out a year or two .
3 | ESTU | Estuary Habitat Studies | Bierman | 123452 | Synthesis Memo #3 - CEERP Adaptive Management and State of the Science (Woodlands funded FY21). | 1400 | 0 | N | 3 | 1 |  |  | 3 |  | 3 | 2 |  | 3 | 3 | 2.5714 | CRITFC: Need to see costs. If just for synthesis can wait NOAA: Have some time to finish IDFW: Given the lack of funds, something like a Synthesis memo could be put off another year. It is difficult to rank this specific item because the cost is unknown. If the cost is high, ID would rank it lower. YN: Conduct analysis at a later time when the budget is more robust.
4 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight - for a contract June 2022 for prep and field work summer 2023. (Field work 2022 funded FY21.) | 1500 | 1000 | N | 5 | 3 |  |  | 5 |  | 5 | 5 |  | 5 | 4 | 4.5714 | CRITFC: need to redo title. This is pretty much just pit troll or monitoring NOAA: Necessary for system survival important to understand GC spill
5 | SYS | Avian Island PIT Detection** | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 100 | 100 | N | 4 | 3 |  |  | 5 |  | 5 | 5 |  | 4 | 2 | 4 | CRITFC: need more detections cheapest and only current option to get NOAA: Necessary for system survival important to understand GC spill IDFW: ID has ranked this fairly high because anything we can do to get more PIT detection/recovery improves precision on reach-level estimates for LGR-BON and MCN - BON
6 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Adams | 122645 | Contract oversight (hydraulic testing, construction in remaining 7 units funded FY21), PDT labor | 1500 | 0 | Y | D | 1 |  |  | 3 |  | 2 | 4 |  | M | M | M | CRITFC: Need more clairty on this and see cost. We have work around and little fish benefit. If low cost then higher score NOAA: Can wait but preference is to get this completed. IDFW: It is unclear why this is mandatory, other than that the Corps awarded the contract before ranking. Given the low budget, ID would have ranked this low YN: Not a high priority at this time.
7 | BON | Bonneville PIT Detection** | Hicks | TBD | Installation - cost being determined | 0 | 0 | N | ? | ? |  |  | 3 |  | 3 | 3 |  | 4 | 4 | 3.4 | NOAA: Low score in a low fund year, high score in a high fund year IDFW: This needs more specifics to receive a rank. PIT detection where at BON? YN: Priority depends on cost and available budget.
8 | BON | BON Serpentine Weir Modifications - NEW | Winters | 376133 | Cost share with lamprey. FY22 design only / construction FY23. | 200 | 0 | N | D | 1 |  |  | 2 |  | 2 | 1 |  | 4 | 4 | 2.3333 | CRITFC: Need to get cost and see if there are cheaper alternatives need to coordinate with Lamprey group. NOAA: Meh for salmon. ODFW: How was this coordinated to dig into minimal budget (e.g., corps agreed to cost share expecting to use CRFM funds pre-budget request?). It seems unsupportable to have Corps manage YN: Have lamprey group prioritize within their budget. I don't know enough about any arrangements with lamprey group.
9 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Kovalchuk | 142630 | Design Documentation Report - develop preferred alternative for debris management in FY22 | 350 | 0 | N | 4 | ? |  |  | 4 |  | 4 | 3 |  | 4 | 5 | 4 | CRITFC: If the Fish Unit work is going to happen regardless if this is done then high priority. But this has to be done prior to TDA fish unit rehab NOAA: Indications are nighttime1hr shutdown or lamprey low flow op could eliminate need YN: If additional funding is available through infrastructure bill this becomes a higher priority.
10 | JDA | John Day Mitigation | Chane | 122434 | Analysis for JDA - Limited Reevaluation Report / Umatilla Hatchery Trip Report | 0 | 0 | N | 2 | ? |  |  | 4 |  | 3 | 2 |  | 2 | 1 | 2.3333 | CRITFC: Need more info NOAA: has hatchery mitigation always been funded by CRFM? Could effectivley siphen funds away from ESA listed wild fish. YN: High prioritity if additional funds become available.
11 | SYS | FCRPS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support | 500 | 350 | Y |  | 1 |  |  | 3 |  | 2 | M |  | M | M | M | NOAA: This never used to be a line item. Were they always funded by CRFM or some other source? YN: Budget seems high relative to the number of projects being implemented.
12 | SYS | Inland Avian Predation | Kelly | 328188 | Blalock Island - Reservoir operations/monitoring, year 2 in 2022. | 20 | 0 | N | 3 | 1 |  |  | 5 |  | 4 | 4 |  | 5 | 4 | 3.7143 | CRITFC: Does this need to be inplace prior JDA pool operation if not then lower score NOAA: Litigation issue YN: Low cost to continue evaluation.
13 | SYS | Cooling water structures - potential locations: JDA MCN IHR LMO |  |  | Cooler water addition to fish ladders at projects | 0 | 0 |  | 5 |  |  |  | 4 |  | 3.5 | 5 |  | 3 | 3 | 3.9167 | CRITFC: important to get moving on NOAA: One of the more important issues with climate change. Has a significant impact on SR sockeye and Summer Chinook. IDFW:This should get a high priority to start the process for LMN YN: New. No background. Important if budget can support it.
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | Kelly | 464428 | Acoustic and Laser Deterrent system - permanent placement | 75 | 75 | N | 2 | 1 |  |  | 3 |  | 4 | 1 |  | 3 | 5 | 2.7143 | CRITFC: if high cost lower score NOAA: Not very optomistic this is going to work. Wire array more beneficial. YN: No budget provided. Not a priority until work plan is better developed.
15 | IHR | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Contract oversight, labor | 125 | 0 | Y | D | 1 |  |  | 2 |  | 2 | M |  | M | M | M | CRITFC: ballon tag study can wait IDFW: It is unclear why this is mandatory, other than that the Corps awarded the contract before ranking. It is in the 2020 ROD, but so are other things. Given the low budget, ID prefers to defer this in favor of moving ladder cooling structures forward for LMN at least. YN: High priority for COE but low priority for F&W. Can this work be put off until a larger budget is available?
16 | LGO | Little Goose Adult Ladder Temperature Mitigation | Juhnke | 456609 | Added new Work Item for Cooling Intake Sluice Gate - sluice gate to allow fish to egress out of cooling structure. | - | - | N | 3 | ? |  |  | 4 |  | 3 | 2 |  | 3 | 3 | 3 | CRITFC: look at cost, important but few adults have been observed in NOAA: Good to get done but recommend delay in low fund year
17 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) | Martin | 372857 & 493013 | Funding for contract oversight, labor in FY22. | 400 | 0 | Y |  | ? |  |  | 5 |  | 4 | M |  | M | M | M | NOAA: Could be delayed? YN: Need clarity, could be crucial to get this done.
18 | LGR | Lower Granite Turn Pool Gate - NEW |  | 372529 | Shad deterrence, automating hoist system to make more usable | 60 | 0 | N | 4 | 1 |  |  | 2 |  | 3 | 3 |  | 4 | 4 | 3 | NOAA: Very important BiOp item but can be delayed in low funding year. YN: Could be important with another warm summer, not enough funding to accomplish much in the way of shad deterrence.
19 | SYS | FCRPS CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. | 80 | 50 | Y |  | 1 |  |  | 4 |  | 2 | M |  | M | M | M | NOAA: This never used to be a line item. Were they always funded by CRFM or some other source?
20 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | - | - | N | 3 | ? |  |  |  |  | 2 | 1 |  | 2 | D | 2 | YN: Not enough information.
21 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | - | - | N | 3 | ? |  |  |  |  | 3 | 2 |  | 2 | D | 2.5 | YN: Not enough information.
22 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | - | - | N | 4 | ? |  |  | 4 |  | 2 | 1 |  | 1 | D | 2.4 | YN: No budget provided. Not a priority until work plan is better developed.
23 | LGO | Little Goose Adult Ladder PIT Feasibility | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 | - | - | N | 3 | ? |  |  | 3 |  | 1 | 1 |  | 1 | D | 1.8 | YN: No budget provided. Not a priority until work plan is better developed.
24 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW | - | - | N | 3 | ? |  |  | 4 |  | 1 | 1 |  | 4 | D | 3.5 | YN: No budget provided. Not a priority until work plan is better developed.
25 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Kelly | 473224 | Testing and monitoring using the newly installed pit tag detection system installed on spill bay #1 at Lower Granite - study oversight - no funding need FY22
26 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Closeout in FY21 - no FY22 funding need
27 | LGR | Lower Granite Spillway PIT Detection | Juhnke | 368299 | Final installation of access platform and closing out in FY21
28 | MCN | McNary Steelhead Overshoot | Zelch | 479912 | Study completing
29 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - FY21 was Final Year of CRFM funding under ROD
30 | MCN | McNary Top Spill Weir (TSW) Permanence | Bonafilia | 398029 | Final work and closeout in FY21
31 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Planned for Closeout in FY21 - Real estate transfer process | - | -
Note: **Means co-funded with BPA

## FY22 Ranked Order-Sept
CRFM FY19 RANKING SPREADSHEET
| 2023-04-15 | FY22 Budget $75.491 M
Updated By: I. Royer
#REF!
Line # | Project Location | Measure | FY22 budget | FY22 Workplan Cumulative | SCT Avg Score (Sept)
Willamette
1 | Willamette | Total - Willamette | 73030 |  | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 0 |  | M
FCRPS
6 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 130 |  | M
11 | SYS | FCRPS CRFM Program Management (NWP) | 275 |  | M
15 | IHR | Ice Harbor Turbine Passage Survival Program | 0 |  | M
17 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) | 2200 |  | M
19 | SYS | FCRPS CRFM Program Management (NWW) | 18 |  | M
4 | SYS | Lower Columbia River Juvenile Survival Studies | 0 |  | 4.5714
5 | SYS | Avian Island PIT Detection** | 0 |  | 4
9 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 150 |  | 4
13 | SYS | Cooling water structures - potential locations: JDA MCN IHR LMO | 0 |  | 3.9167
12 | SYS | Inland Avian Predation | 0 |  | 3.7143
24 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | 0 |  | 3.5
7 | BON | Bonneville PIT Detection** | 0 |  | 3.4
16 | LGO | Little Goose Adult Ladder Temperature Mitigation | 0 |  | 3
18 | LGR | Lower Granite Turn Pool Gate - NEW | 0 |  | 3
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | 0 |  | 2.7143
3 | ESTU | Estuary Habitat Studies | 0 |  | 2.5714
21 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | - |  | 2.5
22 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | - |  | 2.4
8 | BON | BON Serpentine Weir Modifications - NEW | 0 |  | 2.3333
10 | JDA | John Day Mitigation | 0 |  | 2.3333
20 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | - |  | 2
23 | LGO | Little Goose Adult Ladder PIT Feasibility | 0 |  | 1.8

## FY21 Ranking Sheet
CRFM FY21 RANKING SPREADSHEET |  |  | Updated By: I. Royer |  | 2021-06-15
|  | FY21 Pbud $15.377 M | Lamprey $19.937
FY22PBud $3.575 M
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY21 Scope) | FY21 PBud | FY21 Mid Year Lock | FY21 Workplan Preliminary Cumulative | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2021 Average Score | Agency Remarks During Ranking
| Willamette | [20 empty] | District
1 | Willamette |  |  |  | Total - Willamette (NWP) | 3.7 | 10747 | 10747 | Y | [10 empty] | M |  | P
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP)* | 0 | 1864 | 12611 | Y | [10 empty] | M |  | P/W
FCRPS
Total - CRS (NWW/NWP)
3 | ESTU | Estuary Habitat Studies | Bierman | 123452 | Post construction sampling and bathymetry at Woodland Island Section 536 restoration project. Project effectiveness monitoring | 0 | 428 | 13039 | N | 2 | 1 | 3 |  |  |  | 2 | 3 |  | 3 | 4 | 2.5714 | Important to complete final report on past research to inform BiOp (NOAA)
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - Final Year of CRFM funding under ROD | 30 | 30 | 13069 | Y | [11 empty] | M
11 | JDA | John Day Mitigation | Chane | 122434 | Analysis for JDA - Limited Reevaluation Report / Umatilla Hatchery Trip Report | 0 | 170 | 13239 | Y | [11 empty] | M
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Kovalchuk | 142630 | Engineering Design Report - assess debris management alternatives | 0 | 350 | 13589 | N | 4 | 3 | 4 |  |  |  |  | 4 |  | 4 | 4 | M
8 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight | 1500 | 1700 | 15289 | N | 4 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | 4.5
9 | SYS | Avian Island PIT Detection | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 270 | 120 | 15409 | N | 4 | 3 | 4 |  |  |  |  | 4 |  | 4 | 4 | 3.8333
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | Adams | 465995 | Planned for Closeout in FY19 | 0 | 0 | 15409 | NA | [11 empty] | M
13 | SYS | FCRPS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support | 350 | 741 | 16150 | Y | [11 empty] | M
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | Kelly | 464428 | installation of Acoustic and Laser Deterrent system / testing in FY21 with temporary installation / requires permanent placement following testing in FY22 | 1150 | 46 | 16196 | N | 3 | 3 | 4 |  |  |  |  | 4 |  | 3 | 4 | 3.5
15 | MCN | McNary Top Spill Weir (TSW) Permanence | Bonafilia | 398029 | Final work and closeout in FY21 | 0 | 182 | 16378 | y | [11 empty] | m | Important because it is related to McNary steelhead overshoot Research (NOAA)
16 | IHR | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Contract modification of approximately $120k and approximately $70k in labor for field test prep. | 0 | 193 | 16571 | Y | [11 empty] | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | Wik | 469977 | EDC, S&A and contract close out. | 0 | 0 | 16571 | NA | [11 empty] | M
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | Juhnke | 456609 | Added new Work Item and $30k for Cooling Intake Sluice Gate. | 85 | 40 | 16611 | NA | [11 empty] | M
21 | LGR | Lower Granite Spillway PIT Detection | Juhnke | 368299 | Final installation of access platform and closing out in FY21 | 50 | 76 | 16687 | Y | [11 empty] | M
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Kelly | 473224 | Testing and monitoring using the newly installed pit tag detection system installed on spill bay #1 at Lower Granite | 0 | 203 | 16890 |  | 4 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | M
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | Martin | 372857 & 493013 | Funding for contracts and SA/EDC in FY21 | 3500 | 2088 | 18978 | Y | [11 empty] | M
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | Wik | 464431 | Review, closeout, and equipment removal | 0 | 0 | 18978 | NA | [11 empty] | M
31 | SYS | Snake River Adult Sockeye Passage Initiatives | Wik | 461410 | Final report and project close out | 0 | 0 | 18978 | NA | [11 empty] | M | Important work to complete eventually but rank represents relative importance if funding is limited (NOAA). Oregon Defers
32 | SYS | Inland Avian Predation | Kelly | 328188 | Funding needed for Blalock Island - Reservoir operations/monitoring | 0 | 93 | 19071 | N | [11 empty] | M
33 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Closeout in FY21 - possible additional need (litigation) | 1372 | 1276 | 20347 | Y | [11 empty] | M
35 | SYS | FCRPS CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. | 150 | 17 | 20364 | Y | [11 empty] | M
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 20364 | N | 3 | 3 | 4 |  |  |  |  | 3 |  | 2 | D | 3
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 20364 | N | 2 | 5 | 5 |  |  |  |  | 5 |  | 2 | D | NA
41 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | 0 | 0 | 20364 | N | 4 | 5 | 5 |  |  |  |  | 4 |  | 1 | D | 3.8
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Adams | 122645 | Construction contract and A/E contract in FY 21 - two units and testing. Options for 3 additional units could be exercised pending testing. | 0 | 1860 | 22224 | Y | D | D | 3 |  | 3 |  | 3 | 5 |  | 5 | 4 | M
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Planned for Closeout in FY21 - Real estate transfer process | 0 | 10 | 22234 | Y | [11 empty] | M
| BON | Bonneville PIT Detection | Hicks | TBD | On hold at EDR phase pending future need | 2600 | 0 | 22234 | N | 3 | 5 | 4 |  |  |  |  | 4 |  | 4 | 3 | 3.8333
| BON | BON Serpentine Weir Modifications |  | 376133 | Cost share with lamprey
50 | LGO | Little Goose Adult Ladder PIT Feasibility | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 | 0 | 0 | 22234 | N | 4 | 5 | 5 |  |  |  |  | 3 |  | 1 | 1 | 3.1667 | Region Defers until SRWG report Aug 23 2018.
51 | MCN | McNary Steelhead Overshoot | Zelch | 479912 | Spring and fall study to assess overshoot of steelhead at McNary. Contract oversight and close out of 2nd year of study | 0 | 94 | 22328 | N | 5 | 5 | 5 |  | 5 |  |  | 5 |  | 3 | 4 | 4.5714 | Unclear at this point what year study will occur, but there has been an agreement among federal parties to do the study. Needs further development. (NOAA)
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW | 0 | 0 | 22328 | N | 5 | 5 | 5 |  |  |  |  | 3 |  | 4 | D | 4.75
| LGR | Lower Granite Turn Pool Gate |  | 372529
53 | SYS | FCRPS Court Ordered Spill Evaluation | NA | 466539 | NO LONGER REQUIRED | 0 | 0 | 22328
54 | LGR | LGR - Performance verification monitoring | NA | 334888 | Not needed | 620 | 0 | 22328
55 | TDA | John Day PIT | TBD | 454951 | Closeout | 0 | 0 | 22328

## FY21 Ranked Order
CRFM FY19 RANKING SPREADSHEET
| 2021-06-15 | FY21 Pbud $15.377 M
Updated By: I. Chane
#REF!
Line # | Project Location | Measure | FY21 PBud | FY21 Workplan Preliminary Cumulative | SCT Avg Score
Willamette
1 | Willamette | Total - Willamette | 3.7 | 3.7 | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 0 | 3.7 | M
FCRPS
3 | ESTU | Estuary Habitat Studies | 0 | 3.7 | 4
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | 30 | 33.7 | 0
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 0 | 33.7 | 4
8 | SYS | Lower Columbia River Juvenile Survival Studies | 1500 | 1533.7 | 5
13 | SYS | FCRPS CRFM Program Management (NWP) | 350 | 1883.7 | 0
16 | IHR | Ice Harbor Turbine Passage Survival Program | 0 | 1883.7 | 0
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | 0 | 1883.7 | 0
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | 85 | 1968.7 | 0
21 | LGR | Lower Granite Spillway PIT Detection | 50 | 2018.7 | 0
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | 0 | 2018.7 | 5
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | 3500 | 5518.7 | 0
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | 0 | 5518.7 | 0
33 | SYS | Columbia River System Operations (CRSO) EIS | 1372 | 6890.7 | 0
35 | SYS | FCRPS CRFM Program Management (NWW) | 150 | 7040.7 | 0
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 0 | 7040.7 | 4
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | 0 | 7040.7 | 0
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | 0 | 7040.7 | D
49 | #N/A | #N/A | #N/A | #N/A | #N/A
31 | SYS | Snake River Adult Sockeye Passage Initiatives | 0 | #N/A | 0
32 | SYS | Inland Avian Predation | 0 | #N/A | 0
9 | SYS | Avian Island PIT Detection | 270 | #N/A | 4
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | 0 | #N/A | 0
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | 1150 | #N/A | 4
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | 0 | #N/A | D
41 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study | 0 | #N/A | D
15 | MCN | McNary Top Spill Weir (TSW) Permanence | 0 | #N/A | 0
11 | JDA | John Day Mitigation | 0 | #N/A | 0
50 | LGO | Little Goose Adult Ladder PIT Feasibility | 0 | #N/A | 1
51 | MCN | McNary Steelhead Overshoot | 0 | #N/A | 4
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | 0 | #N/A | D