## Sheet1
Planned/Ongoing Action | Concept Number | Title | Average Rank | Proposal Requested? | Funded? | Status
Color Key: Green=Funded; Yellow=Information Gap
Middle Fork
| JPL-14-01-SYS | Evaluation of predation risks for juvenile Chinook salmon in Dexter Reservoir | FY 18: 3.3 | Yes | No | 11/07/17 - Steering Team requested proposal. 12/5/17 - Federal Family will discuss/Corps focused on other aspects of life stage surviavl first. 2/20/18 - Corps clarified at Steering Team that concept is CRFM elgible. Federal Family agreed to defer until LOP survival is better understood, perhaps in FY19. Spring 2020 - This is still on hold pending more informaion on LOP survival and the SDM workshops.
| JPL-15-04-LOP | Behavior, distribution, and passage metrics of juvenile salmonids for LOP Dam | FY18: 4.8 | Yes | Yes | 4/30/19 - Final report provided by PNNL.
| JPL-17-04-LOP | Estimating survival of juvenile Chinook salmon fry in LOP reservoir | FY18: 4.7 | Yes | Yes | 10/13/17 - Steering Team requested proposal. 2018: This study (year 2) was funded and competed in 2018. Note: there were two years of this LOP fry survival study; 2017 and 2018. Both are complete. 7/23/2020 - Corps proposed an FY21 concept paper for an additional study (year 3) which will involve a desktop modeling analysis of the past data to inform if more fieldwork is required.
| JPL-18-XX-LOP | Hydrologic Evaluation of Operations for Improving Downstream Fish Passage at Lookout Point Dam | NA | Yes | No | 5/16/18 - proposal provided. 7/23/20 - Corps updated that the Willamette EIS will evaluate this to assess different operations.
LOP/DEX Downstream Passage Operations - Spring and Fall surface spill | JPL-19-01-LOP | Evaluation of a spring and summer spill operation at Lookout Point Dam for improving juvenile spring Chinook Salmon dam passage | FY19: 4.3 FY20: 3.7 | No | No | 6/25/19 - Steering Team recommended spill operation in spring 2019 without RM&E, which occurred during spring storm. This has not been funded. 8/6/19 - Joint ST/RM&E prioritized, NOAA noted questions; neither team discussed at subsequent meetings to-date. 7/23/20 - The Interim Measures Plan (IM#21) addresses this action. IM#21 prescribes spillway ops for downstream passage during spring and summer, as long as hydrologic conditions allow. Screw traps will be installed to evaluate fish passage.
LOP/DEX Downstream Passage Operations - Delay refill of LOP Reservoir with spring and fall surface spill | JPL-19-02-LOP | Evaluation of delaying refill and spring surface spill operation at Lookout Point Dam for improving juvenile spring Chinook Salmon dam passage | FY19: 3.8 FY20: 3.7 | No | No | 7/2/19 - ST prioritized FY19 for funding; Corps vetting for feasibility. 6/25/19 - Operation not implemented in FY19. Spring hydrology resulted in significant surface spill however. 8/6/19 - Joint ST/RM&E Prioritization, NOAA was going to follow up on some questions. Neither team discussed at subsequent meetings to-date.
Per Corps 3/25/20 Update: Will assess DSP Actions 1-7 through simulation modeling | APH-19-01-MF | Investigation of spring Chinook salmon passage alternatives for the Middle Fork Willamette River | FY19: 3.5 | Yes | Yes | 6/25/19 - Funding in process. 7/23/20 - This is the series of SDM workshops and modeling efforts which are ongoing in 2020.
| APH-17-01-MF | Prespawn mortality of Middle Fork Willamette Chinook salmon: improving trap, transport, and release operations | FY18: 3.0 | Yes | No | 11-20-17 - Proposal presented to RM&E. 7/23/20 - This study was on hold because of the low adult fish return rates. It is now currently being investigated in the Middle Fork SDM modeling efforts.
Upstream Passage above Dexter Dam | APH-17-01-MF | Evaluate the performance of the trap and haul program of adult Chinook salmon at Dexter Trap | FY19: 3.2 | No | No | 6/25/19 - Corps postponed; Equipment needs/logistics could not be processed in time for FY19 study.
| APH-16-04-FAL | Evaluate reintroduction strategies for adult UWR Chinook salmon above Fall Creek | FY18: 3.5 | No | No | 7/23/20 - This was on hold and is now part of APH-10-02 FC Fall Creek post construction evaluation.
Fall Creek Dam upstream fish passage Fall Creek downstream fish passage operations | APH-19-02-FC | Fall Creek adult trap post-construction evaluation | FY19: 4.0 | Yes | FY20: Yes | 6/25/19 - FY19 funding not processed in time. 3/26/20 - FY20 Contracting with OSU (includes pedigree analysis to assess DSP operations). 7/23/20 - FY21 concept paper drafted for year 2 post construction study.
LOP/DEX downstream passage - Head of Reservoir juvenile fish passage | JPL-15-02-SYS | Evaluate the feasibility of in-stream and head-of-reservoir juvenile fish trap and haul above Willamette Project (WP) Dams | FY20: 2.6 | No | No | 7/23/20 - This is on hold pending results from the SMD wrokshops.
LOP/DEX downstream passage - Head of Reservoir juvenile fish passage. | JPL 20-01-LOP | Spatiotemporal sources of mortality in juvenile reservoir-reared UWR spring Chinook salmon: implications for successful downstream passage at Willamette Valley Projects with an emphasis on Lookout Point | FY20: 3.5 | Yes | Yes | 7/23/20 - Study is ongoing; FY21 concept paper drafted for ongoing study in 2021.
North Santiam
Per ST 11/7/17: informs pre-construction design targets | JPL-18-01 | Winter Steelhead Residualism Rate in Detroit Reservoir | FY18: 3.5 | Yes | No | 2-20-18 - NMFS has determined this information would be most useful to gather after Corps has reinstated passage to see if movement through the reservoir is adequate.
| APH 09-01-DET | Evaluate reintroduction strategies for adult UWR Chinook Salmon above Big Cliff and Detroit dams | FY18: 3.5 | No | No | 1-30-18 - Ian will provide updated budget spreadsheet with CRFM elgible concept. 7/23/20 - This study is on hold. APH-19-03 addresses some of objectives (interim strategies) that will inform this.
| APH-18-01-SYS | Evaluation of factors affecting Santiam River winter steelhead recruitment | FY18: 3.3 | No | No | 7/23/20 - This study is on hold; similar to other studies under study code APH-18-01-SYS, it may not be fundable by CRFM.
| APH-18-01-SYS | Objective 1: Establish a cost-effective approach to estimate winter steelhead spawning abundance in the South Santiam | FY18: 4.0 | No | No | 10/13/17 - Corps reported as not fundable by CRFM.
| APH-18-01-SYS | Objective 2: Evaluate winter steelhead hybridization of summer and winter steelhead in the Santiam natural spawning populations following a management action/s expected to significantly reduce hybridization (e.g. reduction in hatchery summer steelhead releases) | FY18: 1.8 | No | No | 7/23/20 - This study is on hold; similar to other studies under study code APH-18-01-SYS, it may not be fundable by CRFM.
| APH-18-01-SYS | Objective 3: Evaluate effects of hatchery-reared non-native trout releases on winter steelhead in Foster Reservoir | FY18: 2.2 | No | No | 7/23/20 - This study is on hold; similar to other studies under study code APH-18-01-SYS, it may not be fundable by CRFM.
| APH-18-01-SYS | Objective 4: Evaluate catch rates, hooking mortality, and associated effects on spawning success for winter steelhead in the North and South Santiam rivers | FY18: 2.5 | No | No | 7/23/20 - This study is on hold; similar to other studies under study code APH-18-01-SYS, it may not be fundable by CRFM.
| APH-18-02-SYS | Effectiveness of near-term actions to reduce pHOS below Willamette Project dams in the Santiam | FY18: 3.3 | No | No | 12/5/17 - Revisit study once changes are made to AFF.
| APH-18-02-SYS | Objective 1:Evaluate pHOS below Foster Dam after improvements to Foster AFF are made leading to increased collection efficiency | FY18: 3.2 | Yes | No | 11/07/17 - Steering Team requested a proposal.
| APH-18-02-SYS | Objective 2: Evaluate what improvements might be made to increase collection efficiency at Minto Fish Facility, and evaluate pHOS below Minto Dam after improvements are made that lead to increased collection efficiency | FY18: 4.2 | No | No | 7/23/20 - This study is on hold.
| APH-18-02-SYS | Objective 3: Reduce hatchery spring Chinook salmon releases below Foster and/or Minto Dams. Evaluate pHOS below these dams in third, fourth and fifth year following the reduction | FY18: 1.0 | No | No | 7/23/20 - This study is on hold.
Interim operation of Detroit Dam for temperature target | APH-18-03 | Evaluation of effects of changes to temperature targets in the North Santiam UWR spring Chinook and winter steelhead | FY18: 4.5 FY19: 3.7 | No | FY18: Yes FY19: No | 10/13/17 - Steering Team requested a proposal. 6/25/19 - Corps postponed - need review of 2018 study results and assess whether additional study needed.
North Santiam Mutiple Actions: 1, 3, 5, 6, | APH-19-01 NS | Eexamining interim outplanting options that will assess temperature, TDG, and current passage conditions at Minto and Detroit | NA |  | Yes | 3/25/20 - Corps added to planning tables.
Release of adult wild fish in the North Santiam BEFORE fish passage is improved at Detroit Dam | APH-19-03 | Evaluate interim management strategies for adult UWR Chinook Salmon at Big Cliff and Detroit dams: above- versus below-dam adult outplanting productivity | FY19: 4.4 | Yes | Yes | 6/25/19 - Funding in process. 7/23/2020 - Funded and ongoing.
Release of adult wild fish in the North Santiam BEFORE fish passage is improved at Detroit Dam | APH-19-04 | Evaluate interim management strategies for adult UWR Chinook Salmon at Big Cliff and Detroit dams: optimizing above-dam spawner distribution | FY19: 2.3 | Yes | Yes | 6/25/19 - Funding in process. 7/23/2020 - Funded and ongoing.
Downstream fish passage design - conveyance method to below dam - for Cougar and Detroit | JPL18-03-HHB | High Head Bypass Fish Passage Investigations | FY18: 2.7 FY19: 4.5 FY20: support | Yes | Yes | 6/4/19 - Reviewed by Steering Team, all supported. 3/26/20 - Corps is proposing Year 2 of PDT study. 7/23/20 - funded by PDT; study to be implemented in fall 2020.
| FMWQ-18-04-SYS | Assessing effects of TDG on Upper Willamette River Chinook salmon and steelhead downstream of Big Cliff Dam | FY18: 4.2 | Yes | No | 7/23/20 - This is IM#6 of the Interim Measures Plan.
Interim actions to manage TDG before fish passage improved at Detroit Dam | FMWQ-18-04-SYS | Interim actions to manage TDG before fish passage improved at Detroit Dam | FY20: 3.3 | No | No | 7/23/20 - This is IM#6 of the Interim Measures Plan.
South Santiam
| APH-09-01-FOS | Evaluate strategies for reintroduction of adult UWR Chinook salmon and steelhead above Foster Dam | FY18l: 3.8 | No | No | 10/13/17 - Corps reported as not fundable by CRFM.
Foster Dam Downstream fish passage - post-effectiveness performance | JPL-11-05-FOS | Evaluation of Foster Dam Juvenile Fish Passage | FY18: 4.8 FY19: 4.8 FY20: 4.9 | Yes | No | 10/13/17 - Steering Team requested a proposal. 7/25/19 - On hold pending weir fix/data needs. 7/23/20 - Engineering improvements for the weir will take longer. IM#9 of the Interim Measures Plan prescribes nighttime spill ops for fish passage. No additional studies identified for FY21.
Upstream fish passage at Foster Dam | APH-15-05-FOS | Evaluation of Foster Adult Fish Trap Performance | FY19: 4.2 | Yes | No | 11/26/18 - On hold/pending PDT design fixes/info needs. 6/25/19 - Still on hold/pending PDT design fixes/info needs. 7/23/20 - Engineering improvements for the weir will take longer. IM#10 of the Interim Measures Plan prescribes spill ops for upstream fish passage. No additional studies identified for FY21.
Reintroduce spring Chinook salmon above Green Peter Dam | APH-17-02-GRP | Evaluate reintroduction and productivity of UWR Chinook salmon above Green Peter Dam | FY18: 4.0 FY20: 3.3 | No | No | 10/13/17 - Corps reported as not fundable by CRFM.
| APH - 19-01 FOS | Evaluation of alternative outplant methods in relation to temperature and spawning success of natural-origin adult Chinook salmon collected at the Foster Adult Fish Facility | NA | Yes | Yes | 6/25/19 - Proposal provided to RM&E team. 6/25/19 - Funding in process. Spring 2020 - Funded and ongoing. APH 19-01-FOS and APH 19-04-FOS were combined into one study.
Upstream fish passage at Foster Dam. | APH-19-04-FOS | Evaluation of Foster Adult Holding and Transport | FY20: ranked by ST; no average | Yes | Yes | 6/4/19 - Ranked by Steering Team; no average. 6/25/19 - Funding in process. Spring 2020 - Funded and ongoing. APH 19-01-FOS and APH 19-04-FOS were combined into one study.
McKenzie
| APH-09-01-CGR | Evaluate strategies for reintroduction of adult UWR Chinook at Cougar Dam | FY18: 4.2 | No | No | 10/13/17 - Corps reported as not fundable by CRFM.
| JPL-17-08-CGR | Evaluation of nets to influence the behavior and distribution of juvenile spring Chinook in Cougar Reservoir cul-de-sac | FY18: 1.7 | No | No | 2018 - The PDT determiend no information is needed. The FSS is being designed to include gudance nets in the future if nets are necessary to collect fish.
| JPL-19-03-SYS | Spatiotemporal distribution of a copepod, Salmincola californiensis that parasitizes juvenile spring Chinook salmon in the Willamette River Basin: implications for fish collection facilities | FY19: 4.2 FY20: 3.7 | Yes | FY 18: Yes FY19: Yes | Study funded in FY18. Supplemental sampling being funded in FY19. 7/23/20 - Study is funded.
Systemwide
| TD-01-08-SYS | Willamette Falls PIT tag detection efficency calibration | FY18: 4.0 | No | No | 10/13/17 - Corps reported as not fundable by CRFM.
| JPL-10-02-SYS | Juvenile salmonid outmigration monitoring above and below WVP reservoirs | FY18: 0 | No | No | 2018 - Corps determined this is monitoring and not related to specific management actions.
| JPL-15-02-SYS | Evaluate the feasibility of in-stream juvenile fish trap and haul above WVP dams | FY18: 4.0 | No | No | 2018 - Not funded; on hold pending additional infomration from other projects and the SDM workshops.
| JPL-18-04-SYS | Effects of acute and chronic stressors on survival and dam passage of juvenile Chinook salmon infected with a parasitic copepod, Salmincola californiensis: implications for fish collection facilities | NA | Yes | Yes | 4/27/18 - Proposal provided for review. 2/21/19 - Draft report of 2018 Pilot Copepodid Field Sampling Update and associated data collections provided.
Remove or modify revetments | FMWQ-18-01 | Evaluation of habitat benefits associated with USACE revetment modification, including potential cold-water refuge enhancement | FY18: 3.8 FY19: 3.4 | FY18: Yes FY19: No | No | 11/07/17 - Steering Team requested a proposal. 1/30/18 - Ian to provide updated budget spreadsheet with CRFM elgible concepts. 2/20/18 - Habitat work not elegible for CRFM funding. 8/7/18 - Alternate path identified. 6/25/19 - on hold pending FY18 and FY19 SWIFT Study results evaluating juvenile habitat and survival.
Mainstem and tributary habitat for wild Chinook and steelhead (non-flow related) | FMWQ-18-02 | Determination of habitat use patterns for rearing and emigrating juvenile spring Chinook salmon and winter steelhead below Willamette Project dams. (This study is on the mainstem AND lower tributaries) | FY18: 4.0 FY19: 3.3 FY20: 4.3 | Yes | FY18: Yes FY19: Yes | 10/13/17 - Corps reported as not fundable by CRFM. 11/07/17 - Steering Team requested a proposal. 6/25/19 - Funding in process for FY18 and FY19 SWIFT studies.
Willamette Project Dam Passage Delayed Mortality | JPL-18-02-SYS | Willamette Project Dam Passage Latent Mortality | FY18: 3.5 FY19: 2.9 FY20: 2.7 | FY18: Yes FY19: No | No | 11/07/17 - Steering Team requested a proposal for FY18. 12/5/17 - Corps noted not being pursued at this time as its view is that information is not needed for post-construction evaluation. 6/25/19 - Corps and NMFS in discussions. Metric needs to be defined. Questions about how this study relates to supporting decision to address the RPA. Unclear to the Corps how this changes performance metrics already establsihed to address NMFS' RPA to avoid jeopardy.
| JPL 20-01-SYS | Spatiotemporal index of infection severity of a copepod, Salmincola californiensis that parasitizes juvenile spring Chinook salmon in the Willamette River Basin | FY20: 3.5 | Yes | Yes | 3-26-20 - Funding in process.
| FMWQ - 18-02 | Fish Sampling for mainstem and tributary habitat capacity model validation | NA | Part of one overarching study RME 11/21/19 | Yes | 1/23/20 - Funded FY20 (SWIFT).
| FMWQ-18-03 | Develop river-scale physical habitat availability models for N. Santiam and S. Santiam | NA | Part of one overarching study RME 11/21/19 | Yes | 1/23/20 - Funded FY20 (SWIFT).
| FMWQ-18-03 | Develop high-resolution bathymetry and river-scale physical habitat availability model for McKenzie River | NA | Part of one overarching study RME 11/21/19 | TBD | Dependent on first two SWIFT studies (FMWQ 18-02 and FMWQ 18-03).
Operational changes for flow and water temperature management discharged from WVP dams | FMQW-18-03-SYS | Willamette River Instream Flow Science Review and Analysis | FY18: 3.7 | Yes | Yes | 10/13/17 - Steering Team requested a proposal. 10/26/17 - Proposal reviewed by RM&E (3 inter-related proposals).