# Fish Passage Plan (FPP) Change Request Form

Change Form # & Title:	19AppA001 – Doble Testing Schedule for 2019

Date Submitted:		December 20, 2018

Project:			NWW Projects

Requester Name, Agency:	Corps NWW

Final Action:			APPROVED – 2/7/2019

FPP SECTION:  Appendix A – Special Project Operations

JUSTIFICATION:  Adds the Doble testing schedule for 2019 to Appendix A.

PROPOSED CHANGES:  [edits to existing FPP text in track changes]

Table A-1. Doble Testing Schedule in 2019.

| Project* | Dates | Outage (Transformer/Units) | Notes |
| --- | --- | --- | --- |
| MCN | Sep 9-13 Sep 23-27 | T4 (Units 7-8) T5 (Units 9-10) | Both Units offline continuously until returned to service. |
| IHR | Jul 22-25 | TW 1,2 (Units 1-2) | Units 1, 2 OOS daily from 0700-1700. |
| LMN | Jul 25 - Aug 3 | T1 (Units 1-4) | All units OOS ≤ 4 hrs on first/last day for clearances. T2 (Units 5-6) RTS at night 1800-0600. Unit 5 will operate at speed-no-load during the day. Longer period scheduled to allow for installation of oil/water separator and overlapping T1 isophase bus inspection. |
| LGS | Aug 5-9 | T2 (Units 5-6) | All units OOS on first/last day for clearances. T1 (Units 1-4) RTS nightly 1800-0530. |
| LWG | Aug 12-17 | T1 (Units 1-4 and 6) | All units OOS 24 hours/day for clearances except Unit 5 will operate for station service power. |

*BON, TDA, JDA have no specific outage for Doble tests (testing is done concurrent with outages for maintenance).

- COMMENTS:

2/8/19 Charles Morrill, WDFW, via email: “Having pre-season schedule is valuable, updates important as season progresses in consideration of relative adult abundance versus historical timing and/or current events and any need for changes.”

RECORD OF FINAL ACTION:  	Approved at the FPOM FPP meeting on 2/7/2019.