# 2026 Fish Passage Plan

# Appendix A

# Special Project Operations & Studies

Table of Contents

1.	INTRODUCTION	1

1.1.	PURPOSE	1

1.2.	SCHEDULE	1

1.3.	SPILL FOR FISH PASSAGE	1

1.4.	ANNUAL NAVIGATION LOCK MAINTENANCE OUTAGES	1

1.5.	TRANSFORMER OUTAGES FOR DOBLE TESTING 	2

2.	BONNEVILLE DAM	3

2.1.	BON SPECIAL OPERATIONS	3

2.2.	BON STUDIES	3

3.	THE DALLES DAM	3

3.1.	TDA SPECIAL OPERATIONS	3

3.2.	TDA STUDIES	3

4.	JOHN DAY DAM	3

4.1.	JDA SPECIAL OPERATIONS	3

4.2.	JDA STUDIES	3

5.	McNARY DAM	4

5.1.	MCN SPECIAL OPERATIONS	4

5.2.	MCN STUDIES	5

6.	ICE HARBOR DAM	6

6.1.	IHR SPECIAL OPERATIONS	6

6.2.	IHR STUDIES	7

7.	LOWER MONUMENTAL DAM	8

7.1.	LMN SPECIAL OPERATIONS	8

7.2.	LMN STUDIES	8

8.	LITTLE GOOSE DAM	9

8.1.	LGS SPECIAL OPERATIONS	9

8.2.	LGS STUDIES	9

9.	LOWER GRANITE DAM	10

9.1.	LWG SPECIAL OPERATIONS	10

9.2.	LWG STUDIES	11

INTRODUCTION

PURPOSE

This Appendix to the annual Fish Passage Plan (FPP) describes special project operations and studies planned to occur during the current year that may affect fish passage at the four Lower Snake River and four Lower Columbia River projects. All special operations and studies will be coordinated with the project and appropriate regional agencies. The Corps RCC will issue a teletype to authorize all necessary operational changes and provide guidance to project operators.

SCHEDULE

All dates defined for special operations and studies are approximate and could shift earlier or later due to a variety of factors, including river flow, contractor schedules, equipment failures, or other real-time conditions. Some studies in this Appendix may not be implemented. Therefore, a final description of studies and outages/operations being conducted will be regionally coordinated prior to April 1 as part of the Corps’ Anadromous Fish Evaluation Program (AFEP) via the Fish Facilities Design Review Workgroup (FFDRWG) and/or the Studies Review Workgroup (SRWG). The Action Agencies will coordinate all significant operational requests and/or schedule changes with fish agencies and tribes through the appropriate regional forum to inform the final decision.

  - SPILL FOR FISH PASSAGE

Spill operations for fish passage will be implemented as defined in the Fish Operations Plan (FOP; included in the FPP as Appendix E), or as otherwise coordinated in-season through TMT.

ANNUAL NAVIGATION LOCK MAINTENANCE OUTAGES

Annual navigation lock outages are scheduled for routine maintenance and inspections, as well as non-routine work (e.g., gate cleaning, structural inspections and repairs, equipment/machinery repair and replacement). The 2026 outage schedule is as follows:

| Project | Lock Outage |  | Project | Lock Outage |
| --- | --- | --- | --- | --- |
| BON | March 2–14 |  | IHR | February 21 – March 28 |
| TDA | March 1–21 |  | LMN | February 21 – March 28 |
| JDA | March 1–21 |  | LGS | February 21 – March 28 |
| MCN | February 21 – March 28 |  | LWG | February 21 – March 28 |

TRANSFORMER OUTAGES FOR DOBLE TESTING

The current year’s transformer outage schedule for Doble testing at the lower Snake River projects and Dworshak Dam is in Table A-1.

At the lower Snake River projects, Doble testing of transformers is required every 3 years to ensure they are functioning correctly and to identify issues that need repair. The testing must be conducted during warm, dry conditions (July–August) and requires an outage of the transformer and associated units. Testing is performed during already scheduled outages to the extent possible and timed to avoid or minimize impacts to fish. Note that in years that Doble testing isn’t required, the project may still require an outage during the same timeframe to perform necessary transformer maintenance and repairs that were identified in previous Doble tests and inspections. For more information on each outage, see project-specific sections 6-9 below.

At Dworshak Dam, required transformer maintenance and Doble testing occurs every two out of three years starting September 21. For more information on Dworshak maintenance and testing, see Appendix I.

Table A-1. Doble Testing Schedule in 2026.a

| Project | Dates | Outage (Transformer & Units) | Notes b |
| --- | --- | --- | --- |
| IHR | July 13-24 | TW3 & TW4 (Units 3, 4) all hours | Remaining available units (2,5,6) operated per FPP priority order. |
| LMN | N/A |  | No Doble Testing in 2026. |
| LGS | August 3–9 | T1 (Units 1-4) continuous; T2 (Units 5-6) first / last day | All units OOS 0500-1700 first and last day with Unit 4 providing station service. Units 1-4 will remain OOS during the continuous T1 outage with Units 5-6 operating per FPP priority order. |
| LWG | August 10-14 | T1 (Units1-4) Continuous T2 (Units 5-6) Daily 0600-1800 | Units 1-4 OOS all hours. Units 5-6 OOS 0600-1800 daily, with Unit 5 providing station service. |
| DWR | Sep 21-25 | T1 (Units 2, 3) all hours | Unit 3 and T1 500kv line outage for Doble. Unit 2 also OOS for T1 outage. |

a. The lower Columbia projects (BON, TDA, JDA, MCN) perform Doble testing concurrent with outages for maintenance and do not have specific outages for Doble tests.

b. OOS = Out of Service (unavailable to operate); RTS = Return to Service (available to operate).

BONNEVILLE DAM

BON SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage and navigation lock maintenance.

BON STUDIES

No studies planned at BON in 2026.

THE DALLES DAM

TDA SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage and navigation lock maintenance.

TDA STUDIES

No studies planned at TDA in 2026.

JOHN DAY DAM

JDA SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage and navigation lock maintenance.

Blalock Islands Operation

- Dates: April 10 – June 1 (or as feasible based on river flows)

- Description: As described in the 2026 Water Management Plan, the John Day Dam reservoir will be held between elevation 264.5 feet and 266.5 feet (an average of 265.5 feet) from April 10 through June 1 (or as feasible based on river flows) to deter Caspian terns from nesting in the Blalock Islands Complex. This operation is per the 2020 CRS BA (page 2-57).

- Impacts to FPP Criteria: None planned. Any modification to FPP criteria will be coordinated through FPOM.

JDA STUDIES

No studies planned at JDA in 2026.

McNARY DAM

MCN SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage and navigation lock maintenance.

Fish Ladder Exit, Entrance, Regulating/Tilting Weir Maintenance

- Dates: Monthly (Long Term)

- Description: The Oil Accountability Program PMs maintenance efforts require the project to operate all equipment monthly and semi-annually to assess oil/grease requirements and to ensure seals do not dry out or stick to shafts. The motors for each weir can be operated during the winter outage to exercise seals.

- Impacts to FPP Criteria: None planned. Minimal impact due to coordination of outages and use of non-peak adult fish passage times. Any modification or deviation from FPP criteria will be coordinated with FPOM.

Spillway Safety Restrictions

- Dates: Year-round (Long Term)

- Description: Due to the overloaded condition of the spillway hoists and cranes, most gates will be operated in a split leaf configuration, which splits the upper gate section from the lower gate section. If a gate is operating in the full gate configuration, where the upper gate section is pinned to the lower gate section, the gate must be set down on seal and tagged out before being approached by personal for work. If hoists adjacent to the hoist being worked on are also operating in a full gate configuration, those gates must also be set down on seal and tagged out. This ensures the safety of personnel and equipment.

- Impacts to FPP Criteria: Spill pattern changes to support spillway cranes and potential intermittent spill pattern changes due to unforeseen hoist maintenance. Any modification or deviation from FPP criteria will be coordinated with FPOM.

Outages for Digital Excitation/Governor Upgrades.

- Dates: FY22 – FY26

- Description: Replacing Exciters and Governors with digital systems to upgrade generators to current electrical standards, Mechanical Governor Upgrades, Power House Control Systems Upgrades, Isophase, HV Bus and XJ Switch upgrades.

- Impacts to FPP Criteria: Unit priority will be affected, and commissioning requirements will require exceeding 1% during testing of Over Speed Protection, Upper and Lower Excitation Limits, Mechanical Governor Response Times, and other reliability tests necessary. Some specific testing will require raising ESBSs during testing, especially when determining new Generator Capability Curve data. Due to the extended period of these contracts, raising ESBSs and exceeding 1% may occur at any time of year.

Waterfowl Nesting

- Dates: April through July (annually)

- Description: Since 1982, McNary pool is operated for waterfowl nesting on Lake Wallula annually from late April through early July. During this operation, the McNary pool may be restricted to an operating range of 337’–340’ elevation. Pool elevations are also operated in the range of 338.5’–339.5’ for 4-6 hours during daylight hours at least once every 4 days.

- Impacts to FPP Criteria: None. Provided for informational purposes only.

Transformer Gasket Replacement, Capitol Project

- Dates: April to October

- Description: Transformer gasket replacement will occur with associated unit outages.

- Impacts to FPP Criteria: When a unit is out of service for transformer gasket replacement, the next available unit in the priority order will be operated.

Outages for Turbine 14 Replacement

- Dates: 2026-2027

- Description: Replacement of main unit turbine runners. This upgrade will increase each units Megawatt (MW) output. Ancillary support systems will also be upgraded during main unit outages to support higher unit ratings.

- Impacts to FPP Criteria: Unit priority will be affected. Pre-operational testing and commissioning requirements will require exceeding the previous 1% criteria during multiple functional tests. Additionally, pre-operational tests and commissioning will require raising ESBSs for load rejection testing at quartile percentages. Pre-operational testing is scheduled for 2 weeks. Commissioning is expected to last approximately 1 month. Due to the extended period of this contract, raising ESBSs and exceeding 1% criteria may occur at any time of the year.

MCN STUDIES

No studies planned at MCN in 2026.

ICE HARBOR DAM

IHR SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage, navigation lock maintenance, and Doble testing.

Unit 1 Turbine Runner Replacement

- Dates: Ongoing through 2026

- Description: Unit 1 is out of service through 2026 to replace the runner. After the unit is returned to service (currently scheduled late 2026), commissioning will require full load rejection testing (10 days), which needs to be completed with no submerged traveling screens (STS) installed.

- Impacts to FPP Criteria: While Unit 1 is out of service and unavailable for operation, the project will operate the next available unit in the FPP priority order. Full load rejection testing will be coordinated with FPOM via a separate MOC.

Unit 3 & 4 outage for XWO breaker maintenance

        - Dates: June 29 -30

        - Description: Units will be out of service to allow for crane work while removing XWO breaker.

        - Impact to FPP Criteria: None, while the units are out of service the project will operate the other available units in the FPP priority order.

Doble Testing (see section 1.5 above for more information)

- Dates: July 13-24

- Description: The outage in 2026 is required to perform Doble testing of TW3 and TW4, which will take Units 3, 4 out of service continuously during testing (Unit 1 will already be out of service for runner replacement). Remaining available units 2, 5, 6 will be operated per FPP priority order.

- Impacts to FPP Criteria: None. Since Ice Harbor has multiple transformer banks and transmission lines and redundant switching capability, remaining available units will be available and operated pursuant to FPP priority order.

Spillway 3 & 4 Outages

        - Dates: August 31 – October 9

        - Description: Spillways at Ice Harbor are inspected every five years with two bays being inspected per year, anodes are being installed to prolong the life of the spillway gates.

        - Impact to FPP Criteria: none, two spill bays will be unavailable during the time of the inspection. The inspection is scheduled for after the end of summer spill and will not affect fish passage.

RSW Dive inspection

        - Dates: September 21-27

        - Description: The RSW is inspected every three years assess the condition of the structure and seals, during this time, all spill must be stopped to minimize speed of forebay currents. The intent for this inspection is to use ROV’s instead of divers, minimizing effect on operations.

        - Impacts to FPP Criteria: None, by utilizing ROVs for this inspection, work times could be scheduled after the 4-hour spill window in the morning. In the event of a need to resume spill, ROVs could be retrieved and spill resumed with only a minimal delay.

IHR STUDIES

No studies planned at Ice Harbor Dam in 2026.

LOWER MONUMENTAL DAM

LMN SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage, navigation lock maintenance, and Doble testing.

Lower Monumental Head Gate Rehab

        - Dates: Ongoing through 2029

        - Description: Under the BPA Large Cap Program, parts and materials have been acquired to rehabilitate the head gates at Lower Monumental Lock and Dam.  The work started in December 2012.  To facilitate the process, units will be scheduled out of service to remove or replace head gates.  The head gates will be serviced in the repair pit and then placed back into service.

        - Impacts to FPP Criteria: Deviation from unit priority will be necessary to swap head gates from the unit to the pit.  The duration of the outage is expected to be one day.

Model Validation Testing

        - Dates: January through March

        - Description: Western Electricity Coordinating Council (WECC) requires steady state model validation testing periodically to ensure generating equipment will meet real and reactive power ratings.  All units are tested on a one to two-year cycle.  Tests are also required when equipment is replaced or upgraded.  Tests will require running the unit out of FPP priority and outside the 1% range. Testing can occur any time from January 1 – March 31 and will not occur during peak juvenile fish passage (April 1 – August 31).  Test will preferably be conducted just after annual maintenance but may happen at other times.  Test durations will be minimized to the extent possible and will only be run for the purpose of completing required model validation testing.

        - Impacts to FPP Criteria: May require running a unit out of FPP priority and outside 1%.

Doble Testing (see section 1.5 above for more information)

- Dates: N/A (no outage for Doble in 2026)

- Description: N/A

- Impacts to FPP Criteria: N/A

LMN STUDIES

No studies planned at Lower Monumental Dam in 2026.

LITTLE GOOSE DAM

  - LGS SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage, navigation lock maintenance, and Doble testing.

    - Doble Testing (see section 1.5 above for more information)

- Dates: August 3–9

- Description: The 2026 outage is required to perform T1 Doble testing. T1 (Units 1-4) will be Doble tested and out of service continuously through the entire outage period. T2 (Units 5-6) will be out of service August 3 (first day) and August 9 (last day) from 0500–1700 for LGS 500 kv line isolation allowing prework disconnect and post work reconnect activities. During all other hours, Units 5-6 will be operated per FPP priority order.

- Impacts to FPP Criteria: On August 3 and August 9, all units will be out of service from 0500-1700 and all project outflow spilled.

  - LGS STUDIES

    - Kelt Collection & Reconditioning

        - Dates: April through June.

        - Description: The Nez Perce Tribe (NPT) Department of Fisheries Resources Management will collect wild/natural post-spawned, emigrating steelhead from the separator at Little Goose Juvenile Fish Facility. These fish will be transported to the Nez Perce Tribal Hatchery (NPTH) or Dworshak National Fish Hatchery (DNFH) to be utilized in the kelt reconditioning program.

        - Impacts to FPP Criteria: None.

- LOWER GRANITE DAM

  - LWG SPECIAL OPERATIONS

Special project operations that may require deviations from FPP criteria will be coordinated with FPOM either by inclusion in this Appendix or in-season via a Memo of Coordination (MOC), pursuant to FPP Chapter 1 (Overview). See section 1 above for special operations related to spill for fish passage, navigation lock maintenance, and Doble testing.

    - Head Gate Repair

- Dates: Bi-Monthly (long term)

- Description: This is a long-term program to return head gates to a safe operating condition by adding new roller chain, seals, anodes, and other miscellaneous components. The plan will require brief unit outages throughout the year while transporting rebuilt gates from the turbine units to the repair pit and back. Each swap will take 4–6 hours to complete and occur approximately every 2 months.

- Impacts to FPP Criteria: None anticipated. Head gate movements are expected to take place concurrently with other outages. As the program progresses and fewer head gates need repair, it may require an occasional outage on a priority unit. Available units will be operated pursuant to FPP priority order within ±1% of peak turbine efficiency.

    - ESBS Repair

- Dates: Bi-Monthly (long term)

- Description: This is a long-term program to return ESBSs to a safe operating condition by tearing down, repainting, and rebuilding the screens. The plan will require brief unit outages throughout the year while transporting rebuilt ESBSs from the turbine units to the repair pit and back. Each swap will take 4–6 hours to complete and occur approximately every 2 months.

- Impacts to FPP Criteria: None anticipated. ESBS movements are expected to take place concurrently with other outages. As the program progresses and fewer screens need repair, it may require an occasional outage on a priority unit. Available units will be operated pursuant to FPP priority order within ±1% of peak turbine efficiency.

    - Doble Testing (see section 1.5 above for more information)

- Dates:  August 10-14

- Description: The outage in 2026 requires T1 and T2 (all units 1-6) out of service daily (0600-1800) hours August 10–14. T1 (Units 1-4) will return to service August 14 at 1800 hours. T2 (Units 5, 6) will return to service nightly.

- Impacts to FPP Criteria: Units 1-4 will be out of service all hours, units 5-6 will return to service from 1800-0600 nightly.  During unit outages from August 10 through August 14, all project outflow will be spilled except approximately 8 kcfs through Unit 5 for station service power.

  - LWG STUDIES

    - Genetic Stock Identification (Idaho Department of Fish & Game)

        - Dates: March 1 – June 28

        - Description: Fish collected as part of the Lower Granite juvenile condition sample are used to enumerate and characterize age composition and genetic stock profiles of naturally producing yearling Chinook and juvenile steelhead.  IDFG will sample Monday through Friday through mid-June with a goal of collecting 2,000-5,000 yearling Chinook and juvenile steelhead genetic samples.

        - Impacts to FPP Criteria: None.

    - Kelt Study (Nez Perce Tribe, University of of Idaho, CRITFC)

        - Dates: March 1 – June 29

        - Description: This research investigates steelhead kelt physiology and endocrinology to evaluate the feasibility and success of rehabilitating strategies. Selected kelts collected at Lower Granite are transported by NPT to Dworshak National Fish Hatchery for reconditioning and later release as part of this study.

        - Impacts to FPP Criteria: None.

    - PIT-Tag Adult Wild Chinook and Adult Steelhead for ISEMP-Related Dispersal Monitoring (NOAA Fisheries)

        - Dates: TBD

        - Description: The goal of this project is to PIT-tag up to 4,000 unclipped adult Chinook and 4,000 unclipped adult steelhead collected in the adult trap daily sample for dispersal monitoring.

        - Impacts to FPP Criteria: None.

    - Sampling of Adult Steelhead, Chinook, and Sockeye for Biological Data Collection (IDFG and NOAA Fisheries)

        - Dates: April 4 – December 15

        - Description: Upriver migrating adult steelhead, spring/summer Chinook salmon, and sockeye salmon are collected from the adult trap April 4 through December 15. The goal is to collect 5–20% of adult steelhead, spring/summer Chinook salmon, and sockeye salmon ascending the ladder. Data collection includes fish scales, genetics tissue, sex and length, wild/hatchery composition, and non-adipose clipped hatchery fish assessment. All natural-origin adult steelhead and spring/summer Chinook salmon trapped will be PIT-tagged to estimate headwater tributary escapement. Sockeye salmon may be PIT-tagged in the future to estimate metrics regarding conversion rates. Some steelhead and spring/summer Chinook salmon may be radio-tagged or spaghetti-tagged. This information on adult fish forms the basis for status information used in several forums including BiOp-RPA identified needs.

        - Impacts to FPP Criteria: None.

    - Bull Trout PIT-Tagging and Genetic Sample Collection for USFWS

        - Dates: April 4 – December 15

        - Description: Bull trout will be collected as part of the normal adult trap daily sample and using the adult sort-by-code (SbyC) system to recapture previously PIT-tagged fish.  Untagged bull trout will be PIT-tagged, fin clipped for genetic analysis, and have morphometric data collected including weight and length, etc. Fin clips will be sent to USFWS to determine the fish’s origin.  Previously PIT-tagged bull trout will only have morphometric data collected. All fish will be released back into the adult fish ladder.

        - Impacts to FPP Criteria: None.

    - Subyearling Chinook Parentage-Based Tagging (USGS)

        - Dates: June 1–15 and July 1–15

        - Description: The goal of this project is to determine abundance of unmarked, untagged, natural- and hatchery-origin subyearling Chinook in Lower Granite sample collection. Fin clips will be taken from 30 unclipped, untagged subyearling Chinook each day from June 1-15 and for another two weeks in July depending in fish passage numbers.

        - Impacts to FPP Criteria: None.

    - Collection of Adult Fall Chinook and Coho for Hatchery Broodstock – (WDFW and Nez Perce Tribe)

        - Dates: August 18 until broodstock requirements are met

        - Description: Adult fish are collected in the adult trap. Fall Chinook are transported by WDFW employees to Lyons Ferry hatchery and by NPT employees to Dworshak hatchery.  Coho are transported by NPT and transported to Dworshak hatchery.

        - Impacts to FPP Criteria: None.

“Doble” testing is a common term referring to a power factor test of transformers to measure performance of electrical insulation. Doble is the name of a manufacturer of the test equipment.